## Slide 1: Taking Applications to Production
DAY THREE · MODULE 06
Four gates and twelve steps between a working build and a supported production app, and who owns each one.
06
1 The Paved Path
2 Who you need, and when
3 The long poles
4 UAT through to go-live
Notes: Module 06 closes Day Three. Module 05 gave the room the mechanics: Git, branching, deployment pipelines and promoting a workspace. This module is the rest of the journey: everything between 'it works in DEV' and 'the business is using it in production and HCL can support it'. Frame it for the whole room: tax professionals will request, test and sign off these applications, and technologists will build them. Leadership's goal for this week is a team that can build and ship applications themselves, and this module is the part that is usually learned the hard way.

## Slide 2: By the end of this module you can do six things
MODULE 06 · TODAY
1
THE PAVED PATH
Place any step on the path
Name the four phases, the gate that closes each, and where the twelve steps fall.
2
THE UPSIZE GATE
Accept or refuse a model
Test a model charter, and send it back when a question is still open.
3
THE DEV AND SCOPE GATES
Prove it, don't assume it
Show that the running app answers, and that every state in the model is built.
4
WHO YOU NEED
Open the right approvals
List the approvals each app needs and who owns them.
5
THE LONG POLES
Protect the go-live date
Explain why ESIS and the other slow reviews have to start in week one.
6
THE GO-LIVE GATE
Ship and hand off
Run UAT in TEST, get sign-off, promote and hand off to HCL.
Come back to these six in the wrap-up. They are the test of whether the module worked.
Notes: Read the six outcomes aloud. The top row covers the path and the first three gates. The bottom row covers the approvals, the long poles and the final gate. Nobody needs to memorise the steps. The aim is that everyone knows where they are on the path, what the next gate checks, and whose clock it runs on.

## Slide 3: Module 05 is the mechanics. Module 06 adds the gates.
MODULE 06 · BEFORE WE START
05
DevOps, Governance & Deployment
How a change moves through Git and the pipelines.
1
Git fundamentals
Source control, branches and pull requests
2
Deployment patterns
Pipelines, environments, promoting between workspaces
3
Lab: ship what you built
The lab workflow under source control, promoted upward
06
Taking Applications to Production
When a change is ready to move, and who has to agree.
A branch merges only when the continuous rails pass.
A build is DEV-ready only when the running app answers.
A release goes to PROD only after sign-off and every approval is closed.
The same tag that passed TEST is the one that ships.
Module 05 is how you move a change. Module 06 is when you are allowed to.
Notes: Connect the two modules explicitly so nothing is taught twice. Module 05 covered the mechanics: Git, branches, pull requests, deployment pipelines and promoting between workspaces, plus the lab where attendees shipped their own workflow. Module 06 adds the rules on top of those mechanics. The pipeline from Module 05 is the same one, but now a merge is blocked until the rails pass, DEV is only done when the app answers, and production needs sign-off and closed approvals. If someone asks how to branch or promote, point back to Module 05.

## Slide 4: A working model is where shipping starts
MODULE 06 · THE STARTING POINT
WHAT THE BUILDER RECEIVES
YOU RECEIVE
A working model
Usually one HTML file with invented data. Every screen is clickable and every state can be reached.
AND
A model charter
Purpose, users, assumptions, open questions, and what is deliberately out of scope.
NOT
A specification document
Nobody writes thirty pages. The model is the requirement, and it is more precise than prose.
WHAT THE MODEL IS NOT
Not secure
The login is fake. No auth, no permissions.
Not connected
Every integration is simulated.
Not performant
Fifty invented rows prove a layout, not a query plan.
Not real data
Nothing from any production system.
Not production code
You rebuild it properly, on the standard stack.
Not a free pass
The model changes the input, not the standard.
Nothing in the model is code you keep. Everything in it is a decision you honour.
Notes: This is where the companion material leaves off. The business builds a working model, often a single HTML file with invented data, and hands it to the builder together with a short model charter. For the tax professionals in the room: this is what you will hand over. For the technologists: this is what you will receive. The right side is the honest list. The model is not secure, not connected, not performant, holds no real data, and is not production code. Building on top of it is not allowed. It is a precise statement of what the business wants, and the job is to rebuild it properly.

## Slide 5: Three systems, each on its own clock
MODULE 06 · THE PAVED PATH
Most delivery processes are drawn as a single line. These three run at different speeds, and treating them as one is how work falls through the gaps.
PROCESS
The path work travels
Four phases and four gates, in order. This is the part that looks like a process diagram.
QUALITY CONTROL
The rails and the slow gates
Some checks run on every change. Others run once, on another team's clock, and take weeks.
DOCUMENTATION
The record that flows outward
Phase changes and gate outcomes, for the people who plan rather than build.
WORKFRONT OWNS PROJECT STATE
Phases, gates, approvals and who signed, dates, cost classification and the evidence index. It answers ‘where does the project stand?’
AZURE BOARDS OWNS ENGINEERING DETAIL
Work items, bugs and features, referenced as AB#<id> in commits and pull requests. It feeds Workfront and never speaks for it.
A check that runs on every commit and a review that takes six weeks are different things. Plan them separately.
Notes: This is the mental model for the whole module. There are three systems. The process is the path: four phases and four gates. Quality control is the set of checks: some run on every change and finish in minutes, others are reviews run by another team that take weeks. Documentation is the record that leadership and planners see. The bottom strip shows where each fact lives. Workfront holds project state: gates, approvals, dates and cost classification. Azure Boards holds the engineering work items and feeds Workfront. Neither system copies the other. One pointer between two systems stays accurate, but two copies of the same fact will drift apart.

## Slide 6: Four phases, each closed by a gate you can point at
MODULE 06 · THE PAVED PATH
PHASE 0
Model
The requester builds a working model and writes the model charter.
REQUESTER
Upsize gate
TESTS
The charter has no open questions
PHASE 1
Upsize
The model becomes a real repository on the standard stack, deployed to DEV.
BUILDER
DEV gate
TESTS
The running app answers a request
PHASE 2
Build loop
Features and fixes, with the rails running beside every change.
BUILDER
Scope gate
TESTS
The full flow works, every state reachable
PHASE 3
Release loop
Cut, test, accept in TEST, promote to production.
BUILDER + BUSINESS
Go-live gate
TESTS
Signed off, every approval closed, app verified
No gate is a meeting. Each one tests an artifact or a result that someone can check.
Notes: This is the slide to remember. Four phases, each ending in a gate, and every gate tests something you can point at, not an opinion and not a meeting. Phase 0 belongs to the requester, usually the business. The upsize gate is where the builder gets a say. Phases 1 to 3 belong to the builder. The release loop brings the business back in for UAT and sign-off. The gates have names, not numbers, on purpose. Workfront already uses lettered gates for project governance, and reusing the same labels would suggest the two check the same thing. The next slide places the twelve TDMI steps on this frame.

## Slide 7: The twelve TDMI steps, placed on the four gates
MODULE 06 · THE PAVED PATH
PHASE 0 · MODEL
1
UI draft created
2
UI review with the business
Upsize gate
PHASE 1 · UPSIZE
3
Infra setup (ADO)
4
Dev build
DEV gate
PHASE 2 · BUILD LOOP
5
Test build
6
AI engine build
7
Full flow confirmed
Scope gate
PHASE 3 · RELEASE LOOP
8
UAT in the TEST environment
9
Functional sign-off
11
Moved to production
Go-live gate
10
ESIS approved. Raised in phase 1, closes before go-live. Runs on Enterprise Technology's clock.
12
Docs for HCL handoff. Written at every gate, finished at go-live. Never left to the end.
Steps 1 to 9 run on your clock. Steps 10 and 12 run in parallel, and they decide your go-live date.
Notes: This slide links the TDMI twelve-step list the team already knows to the four gates. Read it column by column. Phase 0 is steps 2 and 3: the UI draft is the model, and the UI review with the business confirms the shape before anything gets locked in. Phase 1 is steps 1 and 4. Infra setup in Azure DevOps can start as soon as the model is accepted, and the dev build is the first deploy. Phase 2 is steps 5 to 7: the test build, the AI engine grounded against real Fabric data, and the full flow confirmed. Phase 3 is UAT, functional sign-off and the move to production. The two amber bars matter most. ESIS, step 10, is not a step you reach at the end. It is raised in phase 1 and runs alongside everything else. The HCL handoff docs, step 12, are written along the way. Those two decide the date.

## Slide 8: You are allowed to refuse the model
GATE 1 · THE UPSIZE GATE
The upsize gate tests an artifact, not an opinion. Every open question in the model charter has an answer, and the out-of-scope list exists.
ACCEPT WHEN
Every question has an answer
Somebody decided, and the decision is written down in the charter.
REFUSE WHEN
A question is still open
An open question is a decision nobody made. If you build anyway, you make it yourself.
NEVER
Answer it for them
Your answer becomes the scope. Send it back. This is the cheapest point in the project to be wrong.
ENFORCED BY THE TOOLKIT
/tdmi:upsize will not start on an open model charter.
It will not answer an open question for you either. The gate is the minimum for any serious project, so the tool holds the line.
Covered in the toolkit section of this module.
The upsize gate is your first and cheapest chance to say no.
Notes: The first gate. Before any real build starts, the model charter is tested: are all the open questions closed, and is there an out-of-scope list? For the tax professionals: this is why the builder may send your model back. It is not a rejection of the idea. It means a decision still needs to be made, and the person who owns the process should make it. For the builders: never answer an open question yourself. If you do, your guess becomes the scope, and nobody knows it was a guess. The upsize skill enforces this, which we cover in the toolkit section.

## Slide 9: Closing the charter once pays off four times
GATE 1 · THE UPSIZE GATE
The charter states purpose, users, assumptions and scope. Four later documents ask for exactly those facts, months apart, from different people.
LATER ARTIFACT | WHAT IT TAKES FROM THE CHARTER | GOES TO
Integration review (ESIS) | Purpose, users and data types | ET&D
Risk-assessment intake | Use cases, business value, user population, data classification | GIS
User documentation | What the application does, and who uses it | TDMI
Acceptance test cases | The workflows a user must be able to complete | TDMI
4
documents from one charter
Two go to Enterprise Technology and security. Two belong to the build team. All four are produced as you go, not under deadline.
Close the charter once and four documents become copy work. Skip it and you write all four from memory.
Notes: This is the business case for the upsize gate. The charter answers purpose, users, assumptions and scope. Months later, the ESIS integration review asks for purpose, users and data types, and the risk assessment asks for use cases, value, user population and data classification. The user documentation and the UAT test cases ask for the same facts again. If the charter is closed, each of these becomes a copy-and-adapt exercise. If it is not, someone is writing them from memory under deadline, usually in the week before go-live.

## Slide 10: The model is a specification. Read it like one.
PHASE 1 · UPSIZE
1
Enumerate the screens
Each screen becomes a route. The model already decided how many there are and what belongs on each.
2
Enumerate the states
Empty, error, success, loading. Every state the model shows must be built, and some are written down nowhere else.
3
Keep the words
Labels, column headings, status names and button text are business decisions. Changing one is a change request.
4
Read the data for shape
Field types, formats and lengths become seeds and test fixtures. Never ship a row of the invented data.
Same habit as Day One: decompose before you rebuild. Reading the Alteryx workflow for inputs, rules and outputs is the same skill as reading the model for screens, states and words.
The temptation is to open the file and start porting. Read it first.
Notes: Once the model is accepted, the builder's first job is reading, not coding. Four passes. List the screens, because each becomes a route. List the states, including empty, error and loading, because for some states the model is the only place anyone wrote them down. Keep the words: labels and status names are decisions the business already made, so changing one is a change request, not a tidy-up. Read the data for its shape and turn it into test fixtures, but never ship the invented rows. Point back to Day One: this is the same decomposition habit we used on the Alteryx workflows.

## Slide 11: The DEV gate: the running app answers a request
GATE 2 · THE DEV GATE
A green pipeline is not proof. A deploy stage can succeed while the application never started, and that has happened.
NOT PROOF
The build passed
A deploy stage can succeed and roll out a placeholder image. Green only means the steps ran.
PROOF
You reached it
The running application answered a request in DEV, and you saw the response.
ALSO CHECK
It is your build
Check the running image digest and the reported version, not the pipeline log.
Step 4 in the TDMI list: first deploy to DEV. It is complete when the running app answers, not when the pipeline shows green.
Every gate in this process tests something you can point at. That is the whole design.
Notes: The second gate closes phase 1. The common mistake is treating a green pipeline as done. A pipeline can succeed and still deploy a placeholder, so green only tells you the steps ran. The proof is that you reached the running application in DEV and it answered. Then confirm it is your build: check the image digest and the version the app reports. For the tax professionals: when someone says 'it's deployed', the right follow-up is 'have you seen it answer?'

## Slide 12: The build loop runs until the full flow is confirmed
GATE 3 · THE SCOPE GATE
1
Work items live in Azure Boards
Referenced as AB#<id> in every commit and pull request.
2
Significant features start as a model
New screens or changed logic get their own small model and charter. A bug fix does not.
3
Continuous rails run on every change
They block the merge, so a problem shows up while the change is still small.
4
Slow gates opened in phase 1 keep running
ESIS and the other reviews progress on their own clocks while you build.
Scope gate tests
Test build promoted into the shared TEST environment (step 5)
AI engine built and grounded against real Fabric data (step 6)
Full flow confirmed end to end, every state reachable, not just the happy path (step 7)
Rails green on the release candidate
Done means every state in the model works, not just the happy path.
Notes: Phase 2 is the build loop, where most of the time goes. Four habits. Work items live in Azure Boards and every commit references one. Significant features get their own small model and charter, so the upsize gate applies again in miniature; a bug fix or a new field does not need one. The continuous rails run on every change, which we cover next. The slow gates opened in phase 1 keep moving in the background. The scope gate closes the loop. It maps to steps 5 to 7: the test build is in TEST, the AI engine is grounded against real Fabric data, and the full flow works end to end, including errors and empty states.

## Slide 13: Eight continuous rails block the merge, not the release
GATE 3 · THE RAILS
RAIL | WHAT BLOCKS THE MERGE
Unit tests | Any failure
Lint, format and type checks | Any failure
Commit-message conformance | Any commit off Conventional Commits
Static code analysis | A new finding above the agreed severity
Dependency licensing | A copyleft or unreviewed licence
Container image scan | A finding above the agreed severity
Secret scanning | Any credential-shaped string. No threshold
Production-data guard | Any production data in the repo. No threshold
CONTINUOUS RAILS
Fast and automated. They run on every change and block the merge. A rail must almost never be wrong, or people switch it off.
EVENT GATES
Slow, with a named owner. Each blocks one named transition. Several take weeks, so none can start at the end.
Two rails have no threshold. A secret or a production record in the repo is never a severity question.
Notes: There are two kinds of quality work, and they should never be drawn on the same line. On the left are the eight continuous rails. They run automatically on every change and block the merge. That is where Module 05's pull requests pick up the rules. Two of them have no threshold at all: a credential in the code or a row of production data in the repository always blocks. This matters for a tax team, because real taxpayer and entity data must never land in source control. On the right are event gates: slow reviews, each with an owner, each blocking one specific transition. The next two slides cover them.

## Slide 14: Every application needs the same approvals
MODULE 06 · WHO YOU NEED, AND WHEN
APPROVAL | TEAM | WHAT IT ASKS FOR | WHEN | NAMED OWNER
Create BAPPID | Enterprise Technology | ServiceNow CMDB record, with a named technical owner | Week one | To be confirmed
Raise ESIS (RITM) | Enterprise Technology | Permissions list, PII and data classification | Week one | To be confirmed
AI intake form | Technology Enablement | Required for any AI use case, through the intake portal | Week one | To be confirmed
TEST admin consent | Enterprise Technology | Delegated scopes. Nothing can be tested without it | Before UAT | To be confirmed
PROD admin consent | Enterprise Technology | Constrained app permissions on the production tenant | Before go-live | To be confirmed
Email relay onboarding | ET&D Messaging | Required for any app that sends email | Before go-live | To be confirmed
UAT and functional sign-off | The business | Users run the manual cycle in TEST. The process owner signs | Before go-live | To be confirmed
Three of these are opened in week one. An approval nobody opened is still open at go-live.
Notes: This is the approvals track, and it ties back to the Day One slide on who owns what. Enterprise Technology owns most of these: the BAPPID record in ServiceNow, the ESIS request, and the TEST and PROD admin consents. Technology Enablement owns the AI intake, which is required for any AI use case. ET&D Messaging owns the email relay, which is easy to forget and needed before go-live for any app that sends notifications. The business owns UAT and sign-off. Three are opened in week one: BAPPID, ESIS and the AI intake. Named owners are still to be confirmed with TDMI, so attendees leave with contacts rather than just team names.

## Slide 15: ESIS is five reviews in sequence, over four to eight weeks
MODULE 06 · THE LONG POLES
Service Management
Engineering
Security
Legal
Operations
4–8
weeks for ESIS approval
Each team reviews after the one before it. The time cannot be compressed at the end.
OPEN THESE IN PHASE 1
Integration review (ESIS): outside teams
Risk assessment: outside teams
Email onboarding: outside teams
AI review: yours alone, and nobody else can start it
A GATE STATES FOUR THINGS
1
Trigger: the event that opens it
2
Owner: whose clock it runs on
3
Blocks: one named transition
4
Artifact: what exists when it closes
Opened at the end, every gap becomes a deadline problem. Opened in week one, it is an engineering problem.
Notes: The long poles decide the go-live date. ESIS is five sequential reviews: Service Management, Engineering, Security, Legal, then Operations. That is four to eight weeks, and it cannot be hurried at the end. Three other slow reviews belong in phase 1 as well: the risk assessment, email onboarding and the AI review. The AI review is the only one entirely in the build team's hands. On the right is a test for whether something is really a gate: it needs a trigger, an owner, what it blocks, and the artifact it produces. If a row in the register cannot state all four, it is either a rail or a wish. The point for planners and leadership: the date is set by when these were opened, not by how fast the team builds.

## Slide 16: The release loop: from cut release to verified app
GATE 4 · THE GO-LIVE GATE
1
Cut the release
Lockstep versions, an annotated tag equal to the manifest, and a readiness record. /tdmi:release-cut does this.
2
Sync the test cases
UAT cases live in git as markdown and sync one way into test management.
3
Accept in TEST
Business users run the manual cycle. The process owner signs and the technical owner countersigns.
4
Promote to PROD
The same tag, after sign-off, with every event gate closed. Then verify the running app.
Go-live checklist
TEST consent granted before UAT
Functional sign-off recorded
ESIS approved
PROD consent and email relay in place
Same tag that passed TEST
Running app verified in PROD
HCL handoff docs complete
Verify the running application in production, not the pipeline log.
Notes: The final gate. Phase 3 has four moves. Cut the release: versions are bumped together, the tag matches the manifest, and a readiness record is produced; the release-cut skill automates this. Sync the test cases from git into test management. Business users run UAT in TEST, which needs the TEST admin consent first; the process owner signs and the technical owner countersigns. Then promote the same tag to production, only when sign-off is in and every event gate is closed, and verify the running app just as you did at the DEV gate. Use the checklist on the right as the go or no-go conversation.

## Slide 17: Git is the source. Test management is a build output.
GATE 4 · UAT
The single most expensive mistake in test management is editing a case directly in the tool.
DO
Edit the markdown
Test cases and requirements live in git. Change them there, then sync one way.
DO NOT
Edit in the tool
An edit in the tool is drift. Copy it back to git before the cycle closes, then sync.
NEVER
Reformat an identity key
Case IDs and name prefixes are permanent after first publish. A reformat duplicates every record.
For tax reviewers: if a test step is wrong, tell the builder rather than fixing it in the tool. The fix belongs in git so the next cycle has it too.
A second sync in a row must report every case unchanged. That is the acceptance test for the sync.
Notes: One rule that saves a lot of rework during UAT. Test cases live in git as markdown, and test management is generated from them. Edit the markdown, not the tool. If someone does edit in the tool, which happens during a busy UAT cycle, copy the change back to git before the cycle closes. Never change a case ID or name prefix after it has been published, because the sync treats it as a new case and duplicates everything. For the business testers: if a step is wrong, raise it with the builder. The check that the sync is clean is that running it twice reports nothing changed.

## Slide 18: The handoff pack is built at every gate, not at the end
STEP 12 · HCL HANDOFF
UPSIZE GATE
Closed model charter
Purpose, users and scope, reused in four later documents
DEV GATE
Running app evidence
The response, the image digest and the reported version
SCOPE GATE
Rails and test results
Scan output, test cases in git, the confirmed full flow
GO-LIVE GATE
Release and approvals
Readiness record, UAT sign-off, ESIS approval and user documentation
HCL handoff
Support takes over an application with its evidence already in place. The final pack is assembled from what each gate produced. Nothing is written from memory.
Evidence is produced along the way, not written afterwards. It exists before anyone asks for it.
Notes: Step 12 is the handoff to HCL for support. It is the step most often left to the end, and that is why it slips. Each gate already produces part of the pack: the closed charter, the evidence that the app ran in DEV, the scan and test results, and the release record with its approvals. If the gates were done properly, the handoff pack is mostly assembly. The exact contents HCL requires should be confirmed with TDMI and Enterprise Technology before the session.

## Slide 19: One rule set in every repo, and six skills to apply it
MODULE 06 · THE TOOLKIT
THE CANON
A CLAUDE.md index plus rules files, at the root of every repository.
Loaded automatically by every Claude Code session
Versioned as a whole. One version, in the index's first line
Never edit it locally. Flag a conflict to the owner
If your repo disagrees, your repo is out of date. Sync it
SKILL | WHEN YOU REACH FOR IT
/tdmi:upsize | A model was accepted and the real build is starting
/tdmi:repo-setup | A repo, new or existing, needs bringing up to the standard
/tdmi:canon-sync | The rules set is missing or out of date
/tdmi:sql-onboard | The app needs a database on a shared server
/tdmi:release-cut | You are cutting a release across a repo pair
/tdmi:qtest-adopt | The repo is adopting test management for the first time
Install the plugin once from the marketplace, then keep it updated. Stale copies are the problem it exists to fix.
Notes: This is where 'ready to build' becomes concrete. AI-assisted development at TDMI runs on Claude Code, and every repository carries the canon: a CLAUDE.md index plus rules files that every session loads automatically. It has one version for the whole set. Nobody edits it locally; if a rule doesn't fit, raise it with the owner. The six skills map onto the path: upsize at the upsize gate, repo-setup and canon-sync in phase 1, sql-onboard when the app needs a database, release-cut and qtest-adopt in the release loop. For the tax professionals: you don't need to run these, but knowing they exist explains why builders can move quickly without skipping the standard.

## Slide 20: The guard checks every command before it runs
MODULE 06 · THE TOOLKIT
RULE | ACTION
A command carrying a PROD identifier | Ask
A command that could make a resource reachable anonymously | Ask
An offensive security-testing tool | Block
pip install | Block, and suggest uv
A write to the org rules set outside the canon repository | Block
A force push to a protected branch | Block
WHAT IT IS
A guard against mistakes. It catches the tired 6pm command that would have touched production.
WHAT IT IS NOT
A security boundary. The plugin can be disabled, and a hook reads a command string; it cannot prove intent. Platform security stays with Enterprise Technology.
A control trusted beyond its reach is worse than none, because everyone stops looking.
Notes: The plugin includes a guard: a hook that checks each command before it runs and each file path before a write. A committed settings file covers sessions without the plugin. Two rules ask for confirmation: anything carrying a production identifier, and anything that could make a resource publicly reachable. Both were already rules that needed a human decision, and the guard moves that decision to the moment of action. Four rules block outright. Be honest about the limits. It is a guard against mistakes, not a security boundary, and it says so. Platform security remains with Enterprise Technology, as we said on Day One.

## Slide 21: Exercise: run the gate review
EXERCISE · MODULE 06
HANDS-ON · 25 MIN The Day Two lab app is heading to production. For each situation, name the gate or rail, and decide: pass, hold or send back. Who acts next?
1
The model charter still lists one open question: should unmapped ad units block the run or only warn?
2
The DEV pipeline is green, but the app URL returns a default placeholder page.
3
It is week six and UAT starts Monday. Nobody has raised ESIS or requested TEST consent.
4
A notebook in the pull request contains a hardcoded connection string with a password.
5
During UAT, a tester corrected a step's wording directly in the test management tool.
6
UAT is signed off and ESIS is approved. The app emails a summary to users, and email relay was never onboarded.
Work in mixed pairs: one tax professional and one technologist. Be ready to defend one call.
Notes: Gate review exercise, about 25 minutes: 15 in pairs and 10 for the debrief. Pair a tax professional with a technologist on purpose. Several situations need both views. Use the app built in the Day Two lab, which gave a workflow inputs, a trigger and an output, so the scenario feels familiar. For each of the six situations, the pair writes three things: which gate or rail applies, whether it passes, holds or goes back, and who acts next. Expect debate on situation 3: the build may be on time, but the date has moved. Answers follow on the next slide; do not show them until most pairs are done.

## Slide 22: Exercise: answers
EXERCISE · MODULE 06
# | GATE OR RAIL | CALL | WHY | WHO ACTS NEXT
1 | Upsize gate | Send back | An open question is a decision nobody made. Don't answer it yourself | The requester and process owner decide and update the charter
2 | DEV gate | Hold | Green means the steps ran. Proof is the running app answering | The builder checks the image digest and version, then redeploys
3 | Long poles | Hold UAT | No TEST consent means no UAT. ESIS adds four to eight weeks | The builder raises ESIS and consent today, and the go-live date is re-planned
4 | Secret scanning rail | Blocked | No threshold. A secret is never a severity question | The builder removes it, uses a managed secret and rotates the password
5 | Go-live gate (UAT) | Fix before close | An edit in the tool is drift. Git is the source | The builder copies the change back to git, then re-syncs
6 | Go-live gate | Hold | Email relay is required before go-live, not after | The builder opens ET&D Messaging onboarding. Should have been phase 1
Four of the six were avoidable in week one. That is the lesson of this module.
Notes: Walk the answers and spend the time on disagreements. 1: send it back; the builder must not decide whether unmapped items block or warn, because that is a tax decision. 2: hold; this is the DEV gate failure described earlier. 3: the most important one. UAT cannot start without TEST consent, and ESIS adds weeks, so the date moves even though the build is on time. 4: the secret scanning rail blocks the merge outright; rotate the credential because it has been exposed. 5: copy the edit back to git before the cycle closes. 6: hold go-live; email relay is a before-go-live item and belonged in phase 1. Situations 1, 3, 4 and 6 could all have been prevented in week one: by closing the charter, opening the slow gates and letting the rails run.

## Slide 23: What good looks like
MODULE 06 · THE STANDARD
✓
Charter closed first
You sent back an open question instead of answering it yourself.
✓
Slow gates opened early
Nothing waits on a six-week review that started last week.
✓
Rails green on every change
A habit with every merge, not a scramble before release.
✓
Evidence produced, not written
The diagram, the scan and the readiness record exist before anyone asks.
✓
One system of record
Workfront owns project state. Boards owns engineering detail and feeds it.
✓
You verified the running app
Not the pipeline log. The response.
Hold each project to these six at every gate review.
Notes: Six habits describe a team that ships well. Read them as a checklist the room can hold each other to. None of them are about coding skill. They are about order and evidence: close the charter, open the slow gates, keep the rails green, let evidence build up as you go, keep one system of record, and verify what is actually running.

## Slide 24: Module 06 in four gates
WRAP-UP
1
UPSIZE GATE
Accept a model only when its charter has no open questions. Never answer one yourself.
2
DEV GATE
DEV is done when the running app answers, not when the pipeline is green.
3
SCOPE GATE
The full flow works, every state is reachable, and the rails are green.
4
GO-LIVE GATE
Signed off, every approval closed, same tag promoted, running app verified.
The artifact you produce along the way is the one you never have to write under deadline.
The delivery map, the gate register and every skill are in the process-canon repository. Named owners to be confirmed with TDMI.
Notes: Go back to the six outcomes from the start of the module and use these four sentences as the summary. Ask the room: which gate would have caught the most problems on a project you have worked on? For tax professionals the usual answer is the upsize gate, and for technologists it is the long poles. Close on the line in the bar: close the charter, open the slow gates, let the rails run, and the final assessment becomes a report rather than a scramble. Point people to the process-canon repository for the delivery map, the gate register and the skills.