## Slide 1: Discuss Databricks SOW & Key Project Topics September 24, 2026

## Slide 2: Agenda
Section | 
1 | Executive Vision & Business Mandate Partnership alignment Strategic Drivers & Program Mission Current State vs Target Lakehouse Architecture
2 | Scope, Metrics & Architectural Foundation Enterprise Ingestion Sizing & Telemetry Scope Data Contract Standardization & The Medallion Architecture Observability & Security Analytics Rationalization
3 | Agile Delivery Model & Factory Execution Moving Beyond Waterfall: The Persona-Based Agile Pod Model End-to-End Modernization Factory Lifecycle (Bronze -> Silver -> Gold) AI Accelerators & Automation Leverage (KPMG Blaze & Claude)
4 | Governance, Commercials & Stakeholders Multi-Party Alliance & Hybrid Commercial Model Program Governance, Cadences & Tracking Integrated Joint Stakeholder Organization & RACI
5 | Integrated Roadmap, Change Freeze & Next Steps Milestone Delivery Roadmap & The 4–6 Week Scope Lock Critical Path & "Welcome Season" Change Freeze Mitigation Day 1 Immediate Priorities & Action Items
To update
Ensure incorporation of:
Deliverables

## Slide 3: Workstream owners – in the table below, the “Lead”
Workstream | EP | EM | Lead
0 | TH | JB | WW
A | DB/NH | MK | JV/DM
B1 | DB/NH | MK/AK | JV/DM
B2 | DB/NH | MK/AK | JV/DM
C | DB/NH | MK/AK | JV/DM
D | RB | JM | DA
E | TH | JB | WW
F | Scicom | Scicom | Scicom
To confirm at 10/6 internal meeting

## Slide 4
Each workstream will require a unique staffing structures to realize our expected outcomes
A: Architecture Review & Remediation |
Sept ’26-Oct ’26
0 – Project Management Office (PMO) | Sept ‘26 – Aug ‘27
Coordinates delivery, dependencies, risks, and governance.
1 Technical PM
1 PM Analyst
E – Organizational Change and Adoption | Sept ’26 - Jul ’27
Drives stakeholder readiness, adoption, and migration planning.
1 OCM Lead
Josie Brucker
1 OCM Manager
1 OCM Analyst
Architecture assessment and pilot outcomes provide the foundation for source rationalization, pipeline
enablement, and analytics modernization.
F: Hypercare | Jul ’27 - Aug ’27
Provides post-deployment support to stabilize operations and accelerate user adoption.
1 Lead Data Engineer
2 Data Engineers
Program Lead
Tom Haslam
Subject Matter Experts
Architecture SME
Niels Hanson
Architecture SME
Deepak Benjamin
ISTS SME
David Muir
Infrastructure SME
Marcus Brakewood
AI SME
Danish Markatia
1 Lead Architect Contributes across workstreams A-D
Cyber Defense
John Haley
Network
Lenny Guardino
Infrastructure
Saul Menkes
CVS
Leaders
1 Data Engineer
1 Platform Engineer
1 Lead Architect
Architect
Shivpratap Singh
1 Team Member
1 Security SME
Platforms
Ken O’Connor
Observability Lead
Josh Sparaga
Data Platforms Lead
Chris Robinson
1 Splunk Lead Ryan Budnik
1 Lead Databricks Engineer
7 Data Engineers (1/Pod)
14 Data Engineers (2/Pod)
Splunk Enterprise
1 Lead Data Engineer
Data Engineers
D: Observability, Availability, and Performance Monitoring Rationalization | Sept ’26 - May ’27
4 Data Engineers (2/Pod)
B1
B2
C: Architecture & Pipeline Enablement | Sept ’26 - May ’27
6 Data Engineers (2/Pod)
B1 / B2: Source Rationalization & Data Contracts | Sept ’26 - Feb ’27
Pod (x7)
4 Data Engineers (1/Pod)
8 Data Engineers (2/Pod)
Pod (x4)
2 Data Engineers (1/Pod)
4 Data Engineers (2/Pod)
Pod (x2)
3 Data Engineers (1/Pod)
6 Data Engineers (2/Pod)
Pod (x3)
Data Owners
Contributes across workstreams B&C
1 Data Architect
20%
60%
57%
70%
67%
33%
Offshore Penetration
To update with slide 3

## Slide 5: Executive Summary Path to finalizing contracts and kicking-off project
Situation: Progress & Considerations
Operational Progress: Planning is continuing to progress, preliminary discussions on Databricks observability/ security schema architecture work and Lovelytics Unity Catalog assessment in progress
Opportunity for Alignment: Signing the agreement will solidify funding alignment, resource allocation, and access, ensuring a smooth project progression
Timeline Pressure: Welcome Season Change Freeze expected to begin ~12/1, presenting a key timeline for landing data sources in Azure
Solution: Alignment
Integrating Timelines: Master schedule has been updated to incorporate feedback from KPMG, CVS, and Scicom and unify milestones
Staffing & Execution: Define delivery roles and workstreams to be ready for kick-off once contracts are finalized
Structured Change Process: Share clear mechanisms in place to handle potential future scope expansions or dataset priority changes
Next Steps: Finalize & Kick-Off
Finalize SOW: Execute signatures to launch project, then schedule kick-off meeting
Secure Funding Buffer: Confirm $9.81M base (w/ 7% expenses) and approve 10% contingency request (to be discussed)
Define Workstream A: Clarify if scope includes automated templates or manual remediation of 200+ existing workspaces
Azure Data Landing Plan: Confirm target for which data sources land in Azure before Welcome Season change freeze
Clarify Workstream B/C/D details: Discuss schema, analytics scope, etc.
Authorize VDI Access: Approve provisional VDI access by mid-Oct. to avoid delays
Confirm Workspaces: Align stakeholder reports on active workspace readiness
Notes: Talking Points:
Acknowledge Progress & Momentum: "We have made significant operational progress with the Agile pods and preliminary architecture work. This 'at-risk' work has been essential to keep the project moving, but it is not sustainable."
Highlight the Immediate Risk: "The most significant risk to our shared success is the lack of a signed SOW. Without it, we face critical challenges with funding alignment, resource allocation, and team access. Most importantly, we risk missing the Dec 1 deadline for data ingestion, which is critical to productivity during the holiday change freeze."
Present the SOW as the Solution: "Signing the SOW this week is the single most important step to de-risk the project. It formalizes our partnership, secures the necessary resources, and unlocks the VDI access our teams need to be productive."

## Slide 6: 1. Technical Approach & Master Timeline

## Slide 7
Workstreams | Oct ’26 | Nov ’26 | Dec ‘26 | Jan ’27 | Feb ’27 | Mar ’27 | Apr ’27 | May ‘27 | Jun ’27 | Jul ’27 | Aug ‘27 | Sep‘27
0 |  |  |  |  |  |  |  |  |  |  |  | 
A |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  | 
Revised Timeline
Pattern Framework Ready
Welcome Season Change Freeze
Project Management
Architecture Assessment
Multi-cloud platform
Ready
HF Migration Complete
Inventory, Routing, Tier 1 Data Landing
Bronze design & validation
Contracts, Templates & Security
Tier 1 rollout & SLA
AI-assisted onboarding & handoff
Tier 2 & hand-off
Silver Design & Validation
Tier 1 Rollout & SLA
Tier 2 & Hand-off
Splunk Indexes Flowing to Bronze
Rationalization & Prioritization
Tier 1 Analytics, Migration, Validation
Security data integrated
Change Management and Power User Migration
User adoption & support
Model Operational
Cutover
support
Transition
& Handoff
CVS Data Lake Milestone
Communication Plan
Tier 1, 2, 3 etc milestones
Remediation Actions
Inventory, Routing, Tier 2 Data Landing
Tier 2 Analytics, Migration, Validation
Tier 3 Analytics, Migration, Validation

## Slide 8: Workstream A Key Objectives
Validate Enterprise Scalability
Confirm the Azure and Databricks platform’s ability to securely and efficiently ingest and process observability and security telemetry at enterprise scale (up to 400 TB/day).
1
Strengthen Security & Governance
Assess the end-to-end security architecture, including Unity Catalog taxonomy, data protection, and Zero Trust controls, to ensure compliance with CVS policies.
2
Identify & Remediate Critical Gaps
Systematically identify and address architectural gaps, misconfigurations, and risks within the current environment to prevent future performance and security issues.
3
Define the Target-State Blueprint
Design and document a robust, scalable target-state architecture and create a strategic Day 1 Go-Live plan and a Day 2 roadmap for future enhancements.
4
Enable Downstream Success
Provide a fully validated, secure, and documented architectural foundation and a formal handoff package to ensure Workstreams B, C, and D can build upon a stable environment.
5

## Slide 9: Workstream A - Architecture Review & Remediation (1/2) Diagnose and Plan – From the SOW and other planning documents
Description: Architecture Assessment
Timing:
Deliverables:
Current-State Architecture Assessment Report (PPT/DOC) summarizing activities performed
Unity Catalog and Data Lifecycle Recommendations (PPT/DOC)
Performance and Scalability Validation Results (PPT/XLS)
Day 1 Go-Live Architecture and Day 2 Roadmap Recommendations (PPT/DOC)
Scope
Assess Azure, Databricks architectures (infrastructure & Medallion), Unity Catalog taxonomy to identify gaps for performance and scalability. Define target-state recommendations, DataOps practices, and risk remediation plan. Execute security and risk remediation plan.
Objective
Validate scalability, security architecture and fitness of the current Databricks platform at enterprise scale and remediate findings.
Key Activities
  Review Unity Catalog Taxonomy, Medallion Architecture, and Data Lifecycle: Databricks data access model (canonical tables, commence Medallion architecture review and discussions, row/column filtering, RBAC/ABAC, workspace isolation, chargeback) across downstream use cases
  Review & Validate Security Architecture: Threat model, Zero Trust controls, data exfiltration controls, pipeline compliance checkpoints, platform attestation (assumption that KPMG will be provided Databricks security implementation guidelines by CVS)
  Review & Validate Encryption Posture: Row-level encryption options, CMK at rest, TLS 1.3 in transit
  Review & Validate Data Protection + Disaster Recovery: Regions, recovery, redundancy
  Review & Validate Scalability and Resilience for High-Volume Data: 400TB/day, 1k+ source, priority users, ingestion (EventGrid & Autoloader), compute storage, and resiliency
  Review & Validate Git & CI/CD Approach: Define target recommendations
  Remediation: Support remediation and/or implementation of key findings; including Lovelytics assessment
  Set-up of security specific workspaces is in scope; resolution of security gaps across entire Databricks platform is currently not in scope
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx
Description: Remediation Actions
Timing:
Deliverables:
Architecture Remediation Tracker and Demonstrated Remediation Evidence (XLS/DOC)
Workstream B-E Handoff Package (PPT/DOC)
A.1
A.2
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Milestone Aligned to SOW §5 and Microsoft ECIF milestone sign-off
Definition of Done (due Dec 7, 2026):
Current-State Architecture Assessment Report delivered and accepted by CVS stakeholders
Security, Governance, and FinOps Findings Register (XLS) created, populated with initial findings, and reviewed with CVS
Unity Catalog and Data Lifecycle Recommendations delivered
Day 1 Go-Live Architecture and Day 2 Roadmap Recommendations presented to and accepted by the CVS architecture team
Definition of Done – 90-day window (due Jan 18, 2027):
Architecture Remediation Tracker created; highest-priority remediation tasks required to unblock Workstream B before the change freeze completed and demonstrated to CVS
Workstream B-E Handoff Package (validated architecture patterns, security standards, operational guidelines) formally delivered to and accepted by downstream workstream leads

## Slide 10: Workstream A - Architecture Review & Remediation (2/2) Diagnose and Plan – Planning
Key “Do Now” activities | Prioritization or Agile Sprint plan with Dependency map Finalize staffing and roles
Upstream Prerequisites | CVS Infrastructure & Access: Timely provisioning of Azure subscriptions and opening of mandatory network ports by Dec 1 Lovelytics Assessment Delivery: Delivery of the current-state Unity Catalog taxonomy and IAM findings from Amit Gonsalves Stakeholder Consensus: Formal agreement from CVS Architecture Leads (Chuck Markham, Sean Elliot, Adam Plotzker) for 26-50 Bronze Delta table model Security & Compliance Guidelines: Provision of CVS threat models, data classification policies, and PHI masking rules from Cyber Defense (Sonia Arista)
Downstream Workstream Hand-offs | To B1 (Source Rationalization): Canonical metadata standards, ODCS contracting templates, and Unity Catalog namespace hierarchy To B2 (Bronze Landing): Validated Auto Loader + Event Grid push notification patterns, ADLS Gen2 folder hierarchy, and throughput validation benchmarks To C (Pipeline Enablement): Medallion data architecture, DLT pipeline templates, PHI masking standards, and Gold workspace isolation models To D (Observability Migration): Confirmed ES and AIOps platform scope boundaries, query performance guidelines, and Silver domain table prerequisites
Epic | 1. Databricks Architecture Assessment & Gap Analysis | 2. Architecture Remediation & Critical Infrastructure Implementation | 3. Architectural Foundation & Handoff to Downstream Workstreams
Features | 1.1: Establish Environment Access & Inventory 1.2: Review & Validate Unity Catalog & Data Lifecycle 1.3: Review & Validate Security Architecture 1.4: Review & Validate Encryption Posture 1.5: Review & Validate Data Protection & Recovery 1.6: Review & Validate Scalability & Resilience 1.7: Review & Validate Git & CI/CD Approach 1.8: Generate Findings Register | 2.1: Clarify & Plan for Dec Change Freeze 2.2: Coordinate Firewall & Network Port Clearance 2.3: Secure Azure Data Flow Authorization 2.4: Implement Tanium & NiFi Ingestion Pathways 2.5: Validate Autoloader Scalability & Prod. Readiness 2.6: Validate PHI Masking Pipeline 2.7: Validate CI/CD Pipeline Production- Grade Standards | 3.1: Define & Align Medallion Architecture 3.2: Finalize Bronze-Layer Table Structure Decisions 3.3: Finalize Silver Taxonomy & Governance Model 3.4: Submit Final Architecture Changes to ARB 3.5: Deliver Day 1 Go-Live Architecture & Day 2 Roadmap 3.6: Prepare & Deliver Workstream B–E Handoff Package 3.7: Conduct Knowledge Transfer
Source: Current KPMG planning, subject to change

## Slide 11: Workstream A – Approach From assessment to an actionable roadmap
Our approach for Workstream A is a multi-phased methodology designed to move from assessment to a concrete, actionable roadmap. We will collaboratively diagnose the current state, design the target architecture, and execute remediation to build a secure and scalable foundation.
1. Discover & Assess
Key Activities
Current-State Documentation Review
Stakeholder Interviews & Workshops
Technical Environment Analysis
Description
We will begin by reviewing all existing architecture, security, and process documentation. This is followed by a series of deep-dive workshops with CVS’s technical SMEs to map the current landscape across seven key domains, including Unity Catalog, security posture, and data lifecycle management.
2. Analyze & Design
Key Activities
Gap Analysis & Findings Registration
Target-State Architecture Design
Remediation & Risk Planning
Description
Based on our findings, we will perform a gap analysis to identify areas of risk and opportunity. We will then design a target-state architecture, create a prioritized remediation plan, and develop a strategic Day 1 Go-Live architecture and Day 2 roadmap.
3. Validate & Remediate
Key Activities
Pilot Validation & Performance Testing
Execute Remediation Plan
Handoff to Downstream Workstreams
Description
The proposed architecture will be validated through performance and scalability testing to ensure it can handle the projected 400 TB/day data volume. We will then execute on the remediation plan and conclude with a formal handoff of the validated architecture and standards to Workstreams B, C, and D.

## Slide 12: Workstream A – Assessment Framework Key components of Databricks Architecture
Data Architecture
Data Modeling
Data Context and Semantics
Data Products
Databricks Architecture
Components
Storage Architecture
ADLS Gen2 Design
Landing-Zone Structure
ADLS Access
Storage Management
Governance, Security and Compliance
Unity Catalog
Identity and Access
Data Governance
Security
Data Ingestion and Processing
Batch Processing
Streaming Processing
Ingestion Technologies
Processing Controls.
Medallion Architecture
Bronze Layer
Silver Layer
Gold Layer
Delta Lake.
Platform and Compute Architecture
Environment Strategy
Workspace Design
Compute Design
Compute Governance
Engineering, Deployment and Operation
Pipeline Framework
CI/CD
Orchestration
Quality, Monitoring and Cost Management
Data Quality
Reconciliation
Monitoring
Reliability and Recovery
Cost Management

## Slide 13: Workstream A – Information Request List Accelerating the assessment and remediation process
To accelerate the assessment and remediation process and meet our critical path timelines, we request the following information and access from the CVS team. Providing these items within the first week is crucial for beating the December 1st change freeze.
Category | Specific Request | Required From
1. Documentation & Current State | All current Azure, Databricks, and Unity Catalog architecture diagrams. Existing security policies, threat models, and data classification standards (e.g., PHI masking rules). Network topology diagrams, including firewall rules and private endpoint configurations. Documentation on the current CI/CD process and Git strategy. The completed current-state Unity Catalog & IAM assessment from the Lovelytics team. | Architecture, Security, and Platform Teams
2. System & Environment Access | Read-only access to Azure and Databricks production and non-production environments for the KPMG architecture team. Provisional VDI access for the core delivery team by mid-October to prevent onboarding delays. Access to Splunk exports, usage data, and source code for key applications to understand data sources. | Platform and IT Operations Teams
3. Stakeholder & SME Availability | A list of primary contacts and nominated SMEs for each technical domain (e.g., Networking, Security, Databricks Platform, Cribl). Confirmed availability for the initial 2-day kickoff workshop and subsequent deep-dive sessions. | Project and Program Leadership
4. Approvals & Governance | Formal agreement from CVS Architecture Leads on the proposed 26-50 Bronze Delta table model. A clear point of contact for timely decisions regarding infrastructure changes and security remediation approvals. | Architecture Review Board and Security Leadership

## Slide 14: Workstream A – Proposed Meetings Operating rhythm for the first two months
To establish a strong operating rhythm, we propose the following meeting schedule for the first two months. This cadence is designed to drive alignment, facilitate rapid decision-making, and ensure all stakeholders remain synchronized.
Meeting | Date(s) | Purpose & Key Attendees
Month 1: October 2026 – Kickoff & Deep-Dive Sessions |  | 
Project Kickoff & Medallion Architecture Workshop (Day 1) | Oct 14, 2026 | Align all stakeholders (CVS, KPMG, Databricks, Microsoft, Scicom) on project goals, scope, and target-state architectural objectives. Review current-state platform and data ingestion sources.
Project Kickoff & Medallion Architecture Workshop (Day 2) | Oct 15, 2026 | Conduct breakout sessions to design the Bronze, Silver, and Gold layers. Agree on the optimal Medallion architecture and define clear, actionable next steps.
Weekly Architecture Deep-Dive Series | Weekly (Tuesdays) | Technical working sessions focused on specific domains (e.g., Unity Catalog, Security Controls, CI/CD). Attendees: KPMG architects and relevant CVS SMEs.
Weekly PMO & Governance Sync | Weekly (Mondays) | Review project status, track RAID log items, manage dependencies, and coordinate cross-workstream activities. Attendees: Project Managers from all parties.
Month 2: November 2026 – Remediation Planning & Change Freeze Prep |  | 
Bi-Weekly Executive Steering Committee | Bi-Weekly (Wednesdays) | Provide executive sponsors with progress updates, highlight key decisions needed, and report on milestone achievements and budget burn. Attendees: Executive leadership from CVS and KPMG.
Change Freeze Critical Path Review | Nov 6 & Nov 20 | A dedicated meeting to track progress on all activities that must be completed before the December 1st change freeze, focusing on data landing and network clearances. Attendees: All workstream leads.
Architecture Remediation Planning Session | Nov 13, 2026 | Review the finalized gap analysis and agree on the prioritization and execution plan for all remediation activities. Attendees: KPMG and CVS architecture and security leads.

## Slide 15: Workstream A - Architecture Assessment Framework - Planning Focus on "how and when" of Milestone A.1 to establish operational clarity and alignment
Milestone A.1 Breakdown & Timeline
Architecture Assessment (Weeks 1–6) Deep-dive evaluation across 7 distinct technical domains to establish a validated technical baseline
Use Case Validation & Pilot (Weeks 7–10) End-to-end telemetry pipeline build, performance testing (validating up to 400 TB/day), and final workspace demonstration
Architecture Remediation Planning (Weeks 4–12) Concurrent gap resolution, security mitigation, and collection of verification evidence
Key Deliverables
Current-State Architecture Assessment Report
Security, Governance, and Findings Register
Unity Catalog and Data Lifecycle Recommendations
Performance and Scalability Validation Results
Day 1 Go-Live Architecture Design & Day 2 Roadmap

## Slide 16: Workstream A - Architecture Assessment Framework – Considerations Focus on lowering risk, highlighting bottlenecks, and demonstrating proactive mitigation
Key considerations for Workstream A:
Recommended Action: Ratifying the SOW this week allows KPMG and Scicom to initiate Week 1 assessment workshops immediately, preserving the narrow window required to beat the Dec 1 change freeze.
VDI Access
(Critical Path)
Dependency: Downstream development is dependent on the completion of VDI onboarding
Mitigation: To ensure a smooth workflow, we recommend CVS authorize provisional VDI access by mid-October to prevent delays.
Welcome Season Change Freeze Compression
Timeline Impact: Delays in assessment completion will shift the pilot build into Q1 2027 due to the welcome season freeze.
Mitigation: To ensure productivity during the freeze, the 5 core telemetry datasets must be successfully ingested before Dec 1
Multi-Party Resource Alignment
(CVS, KPMG, Scicom)
Risk: Misaligned expectations regarding resource availability for the architecture domain deep-dives
Mitigation: Establish a dedicated "assessment calendar" in Week 1 with pre-booked domain-expert workshops
Recommended Action: Signing the SOW will enable KPMG and Scicom to initiate Week 1 assessment workshops, meeting Welcome Season Change Freeze deadline

## Slide 17: Workstream B1 – Source Rationalization and Data Contracts (1/2) “Deciding What Data We Have, Who Owns It, and How It Should Be Labeled” – From the SOW and other planning documents
Scope
Perform rationalization of Splunk, Observability, and Security sources to source families and categories, support definition of data contracts and associated management processes, metadata, ownership and classification.
Objective
Rationalize 2,000+ Splunk source types, rationalizing to approximately 121 logical source families as further described in Section 7.2, and define standardized data contracts, schemas, and a unified metadata model in Unity Catalog.
Key Activities
  Inventory, Classify & Prioritize: Group sources (12k+) by type and score by business value, usage, duplication, complexity; define Tier 1/2/3 priorities
  Define Schema Strategy & Contracts: Evaluate schema approach per source tier: full canonical (e.g., OCSF/ECS/OTEL) for cross-domain detection and compliance; governed native schema for domain-specific sources already consumed without a model; common metadata for discoverability. Establish enforceable contracts (e.g., owner, schema, SLA, quality, classification) with violation workflows in Unity Catalog
  Classify Security & Compliance Boundaries: Support tagging sources by sensitivity (PHI, PII, PCI); define security boundaries for multi-stakeholder canonical tables; determine masking requirements that flow to Workstream C pipeline design; align workspace isolation to data classification
  AI-Assisted Onboarding at Scale: Activation of CVS Claude Code and related agents to infer schema, match against canonical templates, and auto-generate pipeline definitions for Workstream C; measure onboarding velocity; scale beyond linear headcount
  Schema, medallion architecture and pipeline approach needs discussion after internal call this week.
  Cribl pipelines not in scope
  Data landing before welcome season needs discussion.
Milestone
Description: Inventory, Routing, Tier 1 Data Landing
Timing:
Deliverables:
Rationalization Catalog (XLS) including Tier 1 sources
Source Family Taxonomy and Prioritization Framework (DOC/XLS) including Tier 1 prioritization
B.1.1
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Description: Inventory, Routing, Tier 2 Data Landing
Timing:
Deliverables:
Updated Source Inventory and Rationalization Catalog (XLS) including Tier 2 sources
Updated Source Family Taxonomy and Prioritization Framework (DOC/XLS) including Tier 2 prioritization
B.1.2
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Description: Contracts, Templates & Security
Timing:
Deliverables:
Data Contract Template and Contracting Standards (DOC)
Data Classification and Security Boundary Matrix (XLS)
Unity Catalog Metadata Registration Standards (DOC)
B.1.3
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Description: AI-assisted Onboarding & Handoff
Timing:
Deliverables:
BAU Data Governance Handoff Materials (PPT/DOC)
B.1.4
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27

## Slide 18: Workstream B1 – Source Rationalization and Data Contracts (2/2) “Deciding What Data We Have, Who Owns It, and How It Should Be Labeled” – Planning
Notional, to update
Key “Do Now” activities | Establish the Taxonomy Framework and Tier 1 Identification Author and Establish Contracting Standards Secure and Schedule Data-Owner Alignment (Critical Path Dependency) Configure and Validate the AI-Acceleration Tooling
Upstream Prerequisites | Platform & Architectural Prerequisites (from Workstream A) Architecture Validation & Landing Zone Readiness: Validation of the Azure target-state landing zone networking, private endpoints, and infrastructure remediation Lovelytics Assessment Delivery: Provisioning of the current-state Unity Catalog taxonomy and Identity and Access Management (IAM) findings (via Amit Gonsalves) to establish catalog structures and resolve platform gaps Namespace Hierarchy: Definition of the initial Unity Catalog namespace hierarchy to guide how the contracts register metadata
Downstream Workstream Hand-offs | B2 cannot deploy its ingestion infrastructure without the mapping configurations finalized in B1 C relies directly on B1 to build out the Delta Live Tables (DLT) and the Medallion architecture D is responsible for translating 11,199 legacy Splunk SPL queries and dashboards into Databricks SQL E manages the workspace provisioning and user onboarding
Epic | Rationalization Framework & Factory Mobilization | Source Disposition & Contract Authoring at Scale | Unity Catalog Integration & Governance Enforcement
Features | 1.1: AI-Assisted Discovery & Grouping Automation 1.2: ODCS Contract & Prioritization Standards | 2.1: Source Family Disposition (Retain/Consolidate/Retire) 2.2: AI-Powered Contract Generation & Owner Validation | 3.1: Automated Contract Registration in Unity Catalog 3.2: BAU Handoff & New Source Onboarding
Source: Current KPMG planning, subject to change

## Slide 19: Workstream B2 – Databricks Bronze Data Landing (1/2) “Building the Digital Highway to Safely Deliver and Park the Data” – From the SOW and other planning documents
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx
Milestone
Scope
Validate and operationalize data pathways from Cribl/Blob/ADLS into Bronze Delta tables using approved architecture patterns.
Objective
Rationalize 2,000+ Splunk source types, rationalizing to approximately 121 logical source families as further described in Section 7.2, and define standardized data contracts, schemas, and a unified metadata model in Unity Catalog.
Key Activities
  Resolve Bronze Architecture: Define and support loading of Bronze layer for Databricks consumption (ADLS Gen2 landing zone and ingestion into Delta Lake tables via Autoloader); map all ingestion workflows end-to-end; define fork routing per source (legacy analytics platform/ SIEM / Databricks / multiple)
  Validate & Build Pathways: Configure Autoloader + Event Grid per workflow; validate Tanium path (Akamai → Blob → Cribl →ADLS promotion); assess NiFi disposition (retain / consolidate into Cribl / deprecate); test throughput against 5-minute SLA
  Pre-freeze Data Landing: Confirm Cribl worker readiness; activate Tier 1 sources across all paths; confirm critical-path data flowing before Dec freeze (workstream B defines)
Description: Tier 1 Rollout & SLA
Timing:
Deliverables:
Autoloader and Event Grid Configuration Evidence (DOC) for Tier 1 sources
Throughput and SLA Validation Report (PPT/XLS) for Tier 1 sources
Description: Tier 2 & Hand-off
Timing:
Deliverables:
Updated Autoloader and Event Grid Configuration Evidence (DOC) for Tier 2 sources
Updated Throughput and SLA Validation Report (PPT/XLS) for Tier 2 sources
Pre-Freeze Readiness Checkpoint and Handoff Materials (PPT/DOC)
Description: Bronze design & validation
Timing:
Deliverables:
Bronze Architecture and Data Landing Design (DOC/PPT)
Ingestion Routing Matrix and Source-to-Bronze Mapping (XLS)
Pipeline Configuration Documentation (DOC/XLS)
Bronze Table/Partition Design Documentation (DOC/XLS)
B.2.1
B.2.2
B.2.3
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27

## Slide 20: Workstream B2 – Databricks Bronze Data Landing (2/2) “Building the Digital Highway to Safely Deliver and Park the Data” – Planning
Notional, to update
Key “Do Now” activities | Establish Pre-Freeze Technical Readiness & Decisions Align Security & Compliance Guidelines Initiate "Shift-Left" VDI Onboarding Requests Target the Ingestion of 5 Critical Datasets
Upstream Prerequisites | From A2, before data can land into Delta Lake via Autoloader or streaming pipelines, the underlying cloud infrastructure and platform services must be operational From B1, Workstream B2 depends directly on B1 to establish data routing before data reaches Databricks
Downstream Workstream Hand-offs | Workstream C is the most immediate consumer of B2’s output. It cannot transform or enrich data that has not physically landed Workstream B2 provides the sandbox and production data foundations that the analytics migration team needs to validate their SQL conversions To ensure the pipelines run reliably after the KPMG consulting team rolls off, B2 delivers physical operations handoffs for Workstream F
Epic | Architecture Validation & Ingestion Routing Design | Multi-Cloud Ingestion Workflow Verification (WF1–WF6) | Autoloader & Event-Driven Ingestion Automation | Throughput, SLA, & Failover Validation Testing
Features | 1.1: Connectivity & Network Port Clearance 1.2: Bronze Table schema & Partition Design 1.3: Source-to-Bronze Ingestion Routing Matrix 1.4: Apache NiFi Disposition & PHI Chain-of-Custody Assessment | 2.1: WF1 - Tanium Endpoint Telemetry Validation 2.2: WF2 & WF3 - Data Center Ingestion & Splunk HF Cutover 2.3: WF4 & WF5 - Cross-Cloud Telemetry Validation (GCP & AWS) 2.4: WF6 - Azure Native Log Ingestion | 3.1: Event Grid Notification Setup 3.2: Auto Loader Ingestion Configuration 3.3: Ingestion Tiering & Trigger Schedules | 4.1: Volume Ramp & Production Parity Performance Testing 4.2: Peak Burst & Throttle Testing 4.3: Cribl Persistent Queue & Outage Recovery Validation
Source: Current KPMG planning, subject to change

## Slide 21: Workstream B – Approach
Visual of how this work will be done – workshops, interviews, create architecture current state views, target state, gap analysis, recommendations by theme, etc.
Our approach for Workstream B is a phased methodology designed to systematically establish a resilient and scalable data ingestion foundation. We will move from discovery and architectural design to a validated, production-ready pipeline that directly supports the downstream Silver and Gold layers.
1. Define & Architect
Key Activities
Stakeholder Interviews & Workshops
Ingestion Source Analysis
Target-State Architecture Design
Description
We will begin by reviewing all existing documentation on data sources, routing paths (Onum, NiFi), and target ADLS Gen2 landing zones. This is followed by a series of deep-dive workshops with CVS’s technical SMEs (John Haley, Chris Robinson) to map the current ingestion landscape, define data quality contracts, and finalize the architectural patterns for Auto Loader, schema evolution, and the Dead-Letter Queue (DLQ).
2. Implement & Validate
Key Activities
Auto Loader Pipeline Development
Data Contract & DLQ Implementation
Performance & Scalability Testing
Description
Based on our architectural design, we will develop the core PySpark streaming pipelines using Databricks Auto Loader. This includes configuring the cloudFiles source, enforcing a rescue mode for schema evolution to ensure pipeline resilience, and establishing a robust DLQ process to gracefully handle corrupted or malformed records. The pipelines will be rigorously tested for performance to ensure they can handle the projected 150+ TB/day volume.
3. Operationalize & Hand Off
Key Activities
Finalize Operational Runbooks
Handoff to Downstream Workstreams
Establish Monitoring & Alerting
Description
The validated ingestion architecture will be fully documented in operational runbooks and handed off to the teams managing the Silver layer (Workstream C). We will conclude by implementing comprehensive monitoring and alerting on the Bronze pipelines to track data freshness, volume, and quality, ensuring a stable foundation for all downstream analytics.

## Slide 22: Workstream B – Framework
Visual of how this work will be done – workshops, interviews, create architecture current state views, target state, gap analysis, recommendations by theme, etc.
Insert table, what are the things we need first for us to perform the data source rationalization (inventory of data sources, etc). Once we have them, what do we do with it.

## Slide 23: Workstream B – Key Architecture Components
Endpoint and asset
Network and firewall
Identity and access
Cloud and SaaS
Application and infrastructure logs
Vulnerability and threat intelligence feeds
1 Telemetry Sources
Cribl
Onum
Apache NiFi
Azure-native export
Cloud storage delivery
Existing forward pathways
2 Routing & Transport
Source-aligned paths
Environment separation
Time-based folders
Immutable raw payloads
Retention and lifecycle policies
Replay and quarantine zones
3 ADLS Landing
Event Grid/file notification
Databricks Auto Loader
Streaming checkpoints and schema state
4 Event Ingestion
Workstream C: OCSF / Silver transformation
Workstream D: query-conversion validation
Platform Operations: monitoring and support
Governance: lineage, classification and audit
6 Consumers
RAW source fields
Common ingestion metadata
Source identifiers
Ingestion timestamps
Payload and schema version
Quality and processing status
5 Bronze Delta Tables
Cross-cutting foundation
›
›
›
›
›
A metadata-driven control plane for onboarding prioritized telemetry into governed Bronze Delta tables
Data contracts
Owner, format, SLA, classification
Security
Managed identity, groups, least privilege
Reliability
Replay, DLQ, checkpoint recovery
Observability
Freshness, volume, latency, drift
Engineering
Templates, tests, CI/CD, IaC
Operations
Runbooks, escalation, handoff

## Slide 24: Workstream B – Pre-Requisite Components for Scaling
The initial architecture should cover the full source lifecycle, even where detailed design decisions remain open.
1. Source & Contract Readiness
Reconciled inventory and source family
Named owner and downstream use cases
Representative payload and format
Daily volume, burst and arrival profile
Classification and retention
Freshness, quality and schema contract
Routing and filtering ownership
2. Platform & Connectivity
Development and production landing zones
Managed identities and access groups
Network route, firewall and private DNS
ADLS hierarchy and lifecycle control
Event Grid and Auto Loader state
Unity Catalog registration pattern
Compute, secrets and key standards
3. Engineering & Quality
Parameterized ingestion template
Source-specific parser and metadata
Schema evolution and rescued data
Idempotency and duplicates
DLQ, quarantine and replay
Automated unit and integration tests
Load, burst, deployment and rollback
4. Operational Readiness
Freshness and volume alerting
Schema drift and failure monitoring
Cost and capacity controls
Upstream outage behavior
Support owner and escalation path
Operational runbook and SLO evidence
Bronze-to-Silver acceptance
Definition of onboarded: governed, observable, recoverable, supportable and accepted by the downstream consumer.

## Slide 25: Workstream B – Repeatable Source Onboarding Lifecycle
Every prioritized source progresses through the same evidence-based control gates
1
DISCOVER
Owner, family, usage, payload, volume and disposition
›
2
CONTRACT
Schema, classification, retention, quality and SLA
›
3
DESIGN
Route, landing, table, access, DLQ and replay
›
4
BUILD
Config, parser, metadata, tests and monitoring
›
5
VALIDATE
Completeness, parity, failure, replay and throughput
›
6
ACTIVATE
Approvals, live route, alerts, baselines and inventory
›
7
OPERATE
SLOs, drift, incidents, cost and recertification
Gate 1-2
Source approved for engineering
Owner, active use case and minimum contract agreed
Gate 3-4
Implementation ready
Technical design and build evidence complete
Gate 5
Production candidate
Quality, replay, failure and performance evidence accepted
Gate 6-7
Operational service
Approvals, monitoring, runbook and support ownership active
Scale mechanism
Use the same gates, evidence templates and acceptance criteria for each source family, then automate repeatable configuration rather than duplicating pipeline code.

## Slide 26: Workstream B – Scope Boundaries and Integration Responsibilities
Clarify who owns each part of the end-to-end path before source onboarding begins
UPSTREAM PLATFORM OWNERS
Generate and format telemetry
Administer Cribl, Onum and NiFi
Approve production routes and filters
Operate queues and forwarding paths
Provide payload samples and volume profiles
›
WORKSTREAM B CONTROL PLANE
Coordinate source contracts and priorities
Define source-to-Bronze mapping
Implement Auto Loader ingestion
Create governed Bronze Delta outputs
Implement schema evolution, DLQ and replay
Monitor freshness, volume, quality and failures
Deliver runbooks and operational evidence
›
DOWNSTREAM OWNERS
Workstream C: Silver / OCSF transformation
Workstream D: analytics validation
Governance: classification, access and audit
Platform Operations: production support
Consumer teams: use-case acceptance
Boundary statement: Workstream B validates the end-to-end pathway and owns reliable ingestion into Bronze. It does not own every upstream routing platform or downstream Silver and Gold transformation.

## Slide 27: Workstream B – Information Request List
How to accelerate this
To accelerate the Bronze layer implementation and meet our critical path timelines, we request the following information and access from the CVS team. Providing these items within the first two weeks is crucial for preventing delays and beating the December 1st change freeze. Providing these items within the first week is crucial for beating the December 1st change freeze.
Category | Specific Request | Required From
1. Documentation & Current State | All current architecture diagrams for Onum, Apache NiFi, and Cribl Stream. Documentation on existing data contracts, schemas, and data types for the top 20 high-volume data sources. A complete inventory of target ADLS Gen2 landing zones, including directory structures and access policies. | Architecture, Security, and Platform Teams
2. System & Environment Access | Read-access to production configurations for Onum and Apache NiFi to understand current routing and filtering logic. Contributor-level access to a non-production ADLS Gen2 container for development and testing of Auto Loader pipelines. Read-access to the raw log payload samples (Tanium, Falcon, Zscaler). | Platform and IT Operations Teams
3. Stakeholder & SME Availability | A list of primary contacts and nominated SMEs for each ingestion source (e.g., Splunk, Tanium, CrowdStrike, Palo Alto, Zscaler). Confirmed availability for the initial 2-hour kickoff workshop and subsequent deep-dive sessions with ingestion SMEs. | Project and Program Leadership
4. Approvals & Governance | A clear point of contact for timely decisions regarding Bronze table schemas, data retention policies, and DLQ processing logic. Formal agreement from the Architecture Review Board on the proposed use of Databricks Auto Loader and the schema evolution strategy. | Architecture Review Board and Security Leadership

## Slide 28: Workstream B – Proposed Meetings
MK to give a template
Next 2 months?
To establish a strong operating rhythm for Workstream B, we propose the following meeting schedule for the first two months. This cadence is designed to drive architectural alignment, facilitate rapid decision-making, and ensure all ingestion-related dependencies are proactively managed.
Meeting | Date(s) | Purpose & Key Attendees
Month 1: October 2026 – Architecture, Design & Kickoff |  | 
Workstream B Kickoff & Architecture Deep-Dive | Oct 17, 2026 | Align all WS-B stakeholders on the execution plan, review initial data source documentation, and confirm IRL ownership. Attendees: KPMG architects and relevant CVS SMEs.
Ingestion Source Technical Deep-Dive Series | Weekly (Thursdays) | Technical working sessions focused on specific data sources (e.g., Tanium, Onum, NiFi). Define data contracts, schema requirements, and DLQ rules. Attendees: KPMG architects and relevant CVS SMEs.
Month 2: November 2026 – Implementation, Validation & Change Freeze Prep |  | 
Bronze Pipeline Implementation & Review | Weekly (Tuesdays) | Review progress on Auto Loader pipeline development, address technical blockers, and demonstrate completed work. Attendees: All Workstream B technical team members.
Change Freeze Critical Path Review | Nov 6 & Nov 20 | A dedicated meeting to track progress on all ingestion activities that must be completed before the December 1st change freeze, focusing on ADLS landing and network clearances. Attendees: All workstream leads.
Bronze-to-Silver Handoff Sync | Bi-Weekly (Fridays) | Coordinate with Workstream C to ensure the Bronze table outputs align perfectly with the requirements for the Silver core pipelines.

## Slide 29: Workstream C

## Slide 30: Workstream C – Data Architecture and Pipeline Enablement (1/2) The factory – From the SOW and other planning documents
Milestone
Scope
Design and implement scalable Bronze, Silver, and Gold pipelines in Cribl and Databricks, including reusable templates and governed data access via Unity Catalog.
Objective
Enable Project 4 data movement and transformation by building scalable Bronze-to-Silver pipelines, governed data products and reusable Databricks patterns.
Key Activities
  Build & Scale Pipelines: Construct parameterized PySpark/SQL/DLT pipeline templates by source-type group; configure DLT tiering (continuous / triggered / batch) to balance SLA against compute cost; instantiate pipelines from Workstream B contracts and AI-generated definitions
  Implement Governance: Enforce Security & Compliance at Silver. Implement PHI/PII masking (compliance at Bronze); enforce data classification (RESTRICTED -> INTERNAL) via Unity Catalog column-level tags; implement row-level security for multi-owner tables; build audit trail for HIPAA evidence
  Pattern Data Products: Initiate Silver tables with known downstream consumers; apply Data Product metadata (e.g., purpose, owner, consumers, SLO, refresh cadence, relevant Splunk/SIEM meta data); publish in Unity Catalog with documentation and discoverability; remaining Silver tables are governed, retained, searchable but not promoted to Product status
  Enable Self-Service Analytics: Define team-owned Gold workspaces with compute governance, chargeback alignment, and guardrails; provide initial best practices, templates, and Genie configuration for self-service analytics; convert priority SPL to SQL/PySpark (Claude-assisted) as starter content teams deploy into their own Gold space
  Discussion needed: How analytics are to be instantiated in Databricks.
Description: Silver Design & Validation
Timing: Sep 2026 – Jan 2027
Deliverables:
Data Architecture and Pipeline Design (DOC/PPT) summarizing activities performed.
Reusable DLT/PySpark Template Library and Documentation (CODE/DOC).
Enrichment Integration Design and Validation Evidence (DOC/XLS).
Gold Workspace/Self-Service Analytics Design (DOC/PPT).
Description: Tier 1 Rollout & SLA
Timing: Dec 2026 – Apr 2027
Deliverables:
Bronze-to-Silver Pipeline Inventory and Implementation Evidence (XLS/DOC) for Tier 1 source families.
Silver Data Model and Data Product Catalog (DOC/XLS) for Tier 1 source families.
Unity Catalog Governance Configuration Documentation (DOC) for Tier 1 source families.
Pipeline Monitoring, SLO and Operational Runbooks (DOC) for Tier 1 operations.
Description: Tier 2 & Hand-off
Timing: Mar 2027 – Jul 2027
Deliverables:
Updated Bronze-to-Silver Pipeline Inventory and Implementation Evidence (XLS/DOC) including Tier 2 source families.
Updated Silver Data Model and Data Product Catalog (DOC/XLS) including Tier 2 source families.
Updated Unity Catalog Governance Configuration Documentation (DOC) including Tier 2 source families.
Updated Pipeline Monitoring, SLO and Operational Runbooks (DOC) including Tier 2 operations.
Finalized Operational Handoff and Knowledge Transfer Materials (PPT/DOC).
C.3
C.1
C.2
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx

## Slide 31: Workstream C – Data Architecture and Pipeline Enablement (2/2) The factory – Planning
Notional, to update
Source: Current KPMG planning, subject to change
Key “Do Now” activities | Finalize Databricks Delta Live Tables (DLT) & Workspace Architecture Design. Define PHI/PII Masking and Security Requirements. Draft Enrichment Access and Integration Specifications. Pre-populate the Reusable Code Template Catalog. | 
Upstream Prerequisites | Approved Architecture & Unity Catalog Taxonomy (Workstream A) 121 Source Family Taxonomies & Data Contracts (Workstream B1) Operational Ingestion Routes & Bronze Tables (Workstream B2) Network Clearance & Firewall Permissions (CVS Network Team) | 
Downstream Workstream Hand-offs | D: Reusable PySpark and Spark SQL view abstractions mapped to conformed Silver tables D: Transformational mappings (e.g., Splunk accelerated data models translated into optimized, pre-summarized Silver and Gold tables) D: Fully integrated enrichment dimensions (CMDB, identity) allowing security analysts to build cross-domain queries | E: Handover of Spark SQL Cheat Sheets, workspace guides, and Databricks SQL notebook templates to support user onboarding E: Live telemetry metrics reflecting pipeline performance, query response times, and platform adoption statistics F: Reusable DLT code libraries, parameterized templates, pipeline failure recovery runbooks, and SLA/SLO monitoring dashboard templates
Epic | Medallion Architecture Framework & Reusable DLT Templates | Data Quality, Security, & Compliance Governance | Contextual Cross-Domain Enrichments | Gold Analytics Products & Self-Service Enablement | Production Hardening, SLOs, & BAU Operational Handoff
Features | 1.1: Silver Domain and DLT Pipeline Standards Definition 1.2: Reusable DLT Template Development 1.3: Bronze-to-Silver Pipeline Ingestion Scales | 2.1: PHI/PII Masking & HIPAA Pipeline Safeguards 2.2: Unity Catalog Namespace & Access Controls 2.3: Data Lineage & Audit Trail Instrumentation | 3.1: Enterprise CMDB & IT Asset Integration 3.2: Identity & Location Context Feeds 3.3: Threat Intelligence & Vulnerability Enrichment | 4.1: Gold Data Product Curation 4.2: Team-Owned Gold Workspace Allocation & Chargeback 4.3: Legacy Query and Detection-as-Code Translations | 5.1: Pipeline Optimization & Freshness SLA Tuning 5.2: Monitoring, Runbooks, & Alerting Setup 5.3: Reverse-Shadowing & Operational Transition

## Slide 32: Workstream C – Approach Building the Silver and Gold pipeline factory
Workstream C is the core of the Medallion factory, transforming raw Bronze data into enriched, governed, and analytics-ready data products in the Silver and Gold layers. Our approach focuses on building a scalable and reusable pipeline ecosystem.
1. Foundation & Templating
Key Activities
Silver Domain Modeling
Reusable DLT Pipeline Template Development
PHI/PII Masking Pattern Design
Description
We will establish the foundation by modeling 9 Silver domains aligned to engineering teams and developing 30-40 parameterized Delta Live Tables (DLT) templates. A key focus is creating a standardized, auditable pattern for masking PHI/PII data to enforce compliance at the Silver layer.
2. Pipeline Development & Enrichment
Key Activities
Bronze-to-Silver Pipeline Implementation
Integration of Enrichment Sources (e.g., CMDB, Identity)
Data Quality (DQ) Rule Implementation
Description
Using the DLT templates, we will build and scale the ~1,000 pipelines that transform and load data from Bronze to Silver. We will integrate 8-10 critical enrichment sources to add business context and implement robust data quality checks within the pipelines.
3. Product Curation & Enablement
Key Activities
Curation of ~12 Gold Data Products
Gold Workspace & Self-Service Design
Operational Handoff of Pipelines
Description
In the final phase, we will curate high-value Silver datasets into ~12 business-oriented Gold data products. We will design the self-service Gold workspaces and provide operational runbooks and knowledge transfer for the new pipelines to the CVS BAU team.

## Slide 33: Workstream C – Information Request List Requirements and contextual data the pipeline factory depends on
The success of the pipeline factory is directly dependent on clear requirements and access to contextual data sources.
Category | Specific Request | Required From
1. Foundational Inputs | Physically landed and validated Bronze tables for all Tier 1 sources. (Critical Blocker) The finalized Silver domain model and Unity Catalog governance standards from Workstream A. | Workstream B & A
2. Business & Security Logic | Detailed PHI/PII data classification for each source family to drive masking requirements. Business rules for data quality checks (e.g., valid values, nullability, format). Consumer requirements and KPI logic for the 12 planned Gold data products. | Security, Compliance, and Business SMEs
3. Enrichment Data Sources | API endpoints, database credentials, and documentation for the 8-10 enrichment sources (e.g., Enterprise CMDB, Identity & Location feeds, Threat Intelligence). SMEs for each enrichment source to validate integration and data mappings. | Owners of Contextual Data Systems
4. Approvals & Governance | Formal sign-off on the PHI masking patterns before implementation. Acceptance and sign-off on the curated Gold data products by business stakeholders. | Security Review Board & Business Owners

## Slide 34: Workstream C – Proposed Meetings Sprint-based cadence for continuous delivery
This meeting cadence supports an agile “sprint” based approach to pipeline development, ensuring continuous delivery and alignment.
Meeting | Cadence | Purpose & Key Attendees
Month 1: October 2026 – Design & Templating |  | 
DLT Template Design Workshop | Weekly | Whiteboarding and design sessions to build the reusable DLT pipeline templates. Attendees: KPMG and CVS Databricks engineers.
Data Enrichment & Governance Sync | Bi-Weekly | Plan and track the integration of enrichment sources and the implementation of security controls. Attendees: Workstream C leads, Security SMEs, and owners of enrichment data sources.
Month 2: November 2026 – Pipeline Sprints & Backlog Grooming |  | 
Pipeline Sprint Planning & Review | Bi-Weekly | Agile ceremonies to plan the work for the upcoming two-week sprint and review the pipelines completed in the previous one. Attendees: Workstream C delivery pods, project managers, and product owners.
Gold Product Design Session | Bi-Weekly | Define the requirements, schema, and KPI logic for the initial Gold data products. Attendees: Workstream C architects and business analytics stakeholders.

## Slide 35: Workstream D

## Slide 36: Workstream D – Observability, Availability and Performance Monitoring Rationalization (1/2) Monitoring & Analytics – From the SOW and other planning documents
Scope
Objective
Key Activities
Rationalize & rebuild queries, dashboards, and alerts used to monitor various network, asset, identity and application patterns for migration to Databricks (SQL) from Splunk (SPL).
Rationalize and migrate selected analytics from legacy analytics platform Enterprise, legacy analytics platform Core, and AIOps into Databricks, translating queries, accelerated data models, reports and dashboards and deploying them to production for selected stakeholders’ use.
  Inventory & Rationalize: Inventory all content including saved queries (custom/default, enabled/disabled), reports, stats tables, and confirm scoped quantities along with any business priorities or context
  Dependency Mapping & Prioritization: De-duplicate, consolidate, and decompose items to enumerate input sources and dependencies. Coordinate dependencies with data set migration from Bronze to Silver and establish tranches of query migration work split amongst developer pods
  Query Translation, Migration and Refactoring: Migrate decided content from legacy analytics platform Enterprise to Databricks refactoring queries as-needed to accommodate new data schema within Databricks testing and validating functionality as we progress
  Validation & Handover: Perform and workshops, produce documentation, provide final testing and receive stakeholders sign-off on migrated content
Milestone
Description: Rationalization & Prioritization
Timing: Sep 2026 – Dec 2026
Deliverables:
Legacy analytics platform Analytics Inventory and Ownership Matrix (XLS) summarizing activities performed.
Rationalization and Prioritization Assessment (PPT/XLS)
Query Conversion Tracker and Migration Backlog (XLS)
D.1
Description: Tier 1 Analytics Translation, Migration, Validation & Handover
Timing: Oct 2026 – Feb 2027
Deliverables:
Converted Databricks SQL/ PySpark Assets (CODE/DBX) for Tier 1 analytics
Migrated Dashboards, Reports and Alerts (DBX/DOC) for Tier 1 analytics
Recreated Accelerated Data Model Outputs (DBX/DOC) for Tier 1 analytics
Validation Results and Before/After Evidence (XLS/PPT) for Tier 1 analytics
Migration and Handoff Documentation (DOC/PPT) for Tier 1 analytics
Description: Tier 2 Analytics Translation, Migration, Validation & Handover
Timing: Jan 2027 – May 2027
Deliverables:
Converted Databricks Converted Databricks SQL/ PySpark Assets (CODE/DBX) for Tier 2 analytics
Migrated Dashboards, Reports and Alerts (DBX/DOC) for Tier 2 analytics
Recreated Accelerated Data Model Outputs (DBX/DOC) for Tier 2 analytics
Validation Results and Before/After Evidence (XLS/PPT) for Tier 2 analytics
Migration and Handoff Documentation (DOC/PPT) for Tier 2 analytics
Description: Tier 3 Analytics Translation, Migration, Validation & Handover
Timing: Apr 2027 – Aug 2027
Deliverables:
Converted Databricks SQL/ PySpark Assets (CODE/DBX) for Tier 3 analytics
Migrated Dashboards, Reports and Alerts (DBX/DOC) for Tier 3 analytics
Recreated Accelerated Data Model Outputs (DBX/DOC) for Tier 3 analytics
Validation Results and Before/After Evidence (XLS/PPT) for Tier 3 analytics
Final Migration and Handoff Documentation (DOC/PPT)
D.4
D.3
D.2
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx

## Slide 37: Workstream D – Observability, Availability and Performance Monitoring Rationalization (2/2) Monitoring & Analytics – Planning
Notional, to update
Key “Do Now” activities | Convene Splunk Engineering Requirements Alignment: Execute Transpiler & AI Conversion PoC Ingest & Baseline Analytics Inventory | Provisional VDI & Environment Access Requests Draft Integrated Workstream D Agile WBS & Pod Backlog Formalize Pre-Start Commercial & Hour Tracking Guardrails
Upstream Prerequisites | A: Unity Catalog Taxonomy & Namespace Structures A: IAM Profiles & Cluster Compute Policies A: Security, Threat Modeling, and PHI Masking Guidelines A: Isolated Non-Production Workspaces B1: 26 Approved Open Data Contract Standard (ODCS) Contracts B1: Canonical Metadata Dictionary | B2: Validated Ingestion Pipelines (WF1–WF6) B2: Pre-Freeze Live Telemetry Flow C: Governed Silver Domain Tables (9 Domains): Critical Sequencing Blocker C: Column-Level PHI/PII Masking & Row-Level Security (RLS) C:16 Recreated Common Information Model (CIM) Models C: Gold Workspace Isolation Models
Downstream Workstream Hand-offs | E: Validated Databricks SQL queries, interactive Lakeview dashboard templates, SPL-to-SQL cheat sheets, and starter notebook assets . F: Production Databricks Workflows, scheduled query jobs, alert configurations, query execution runbooks, failure triage decision trees, and performance SLO baselines . | 
Epic | Telemetry & Query Rationalization, Inventory, and Prioritization | Tier 1 Security Analytics & Real-Time Threat Detection Migration | Tier 2 Operational, Infrastructure & Dashboard Modernization | Tier 3 Long-Tail Migration, Cutover Governance & Hand-off
Features | 1.1 - Comprehensive Analytics Footprint Discovery 1.2 - Query Dependency & Context Decomposition 1.3 - Redundancy Analysis & Deprecation Pipeline 1.4 - Line of Business (LOB) Domain Clustering 1.5 - Complexity Tiering & Workload Packaging 1.6 - AI Transpilation Factory Setup | 2.1 - Priority Correlation ¦Search Conversion 2.2 - Stateful Risk-Based Alerting (RBA) Refactoring 2.3 - Automated Dual-Platform Parity Testing 2.4 - Alert Notification & SOAR Dispatch Integration 2.5 - SOC UAT & Milestone D.2 Sign-off | 3.1 - Non-Correlation Alert & Saved Search Translation 3.2 - Accelerated Data Model (ADM) Reconstruction 3.3 - Enterprise Observability Dashboard Modernization 3.4 - SQL Warehouse Tuning & FinOps Optimization 3.5 - Infrastructure UAT & Milestone D.3 Acceptance | 4.1 - Long-Tail Query & Ad-Hoc Report Conversion 4.2 - Full-Scale Parallel- Run Verification 4.3 - Workstream E User Wave Enablement Handshake 4.4 - Workstream F Hypercare & Operational Runbook Hand-off 4.5 - Legacy Search Head Schedule Deactivation
Source: Current KPMG planning, subject to change

## Slide 38: Workstream D – Approach AI-assisted migration of legacy analytics to Databricks
Workstream D is a modernization factory focused on migrating high-value analytics from legacy platforms to Databricks. Our approach uses an AI-assisted process to manage the complexity of over 11,000 legacy objects, ensuring a smooth transition for users.
1. Inventory & Rationalize
Key Activities
Comprehensive Analytics Inventory
Query Dependency & Complexity Analysis
Migration Backlog Prioritization
Description
We will inventory all 11,199 scoped objects (queries, dashboards, alerts) from Splunk and AIOps. Using automated analysis, we will map their dependencies, score their complexity (Low, Medium, High), and work with CVS stakeholders to create a prioritized, tiered migration backlog.
2. Translate & Migrate
Key Activities
AI-Assisted SPL-to-SQL Transpilation
Manual Refactoring & Optimization
Dashboard & Alert Reconstruction
Description
The core of the migration involves using an AI-powered “transpilation factory” for the initial conversion of Splunk SPL to Databricks SQL. This is followed by manual refactoring by our engineers to optimize performance and align with the new Medallion architecture. Dashboards and alerts are then rebuilt in Databricks.
3. Validate & Hand Over
Key Activities
Automated Dual-Platform Parity Testing
User Acceptance Testing (UAT) Workshops
Handoff to Change Management & Ops
Description
We will perform automated validation to ensure the output of the new Databricks query matches the legacy Splunk query. We will then conduct UAT workshops with end-users for final sign-off before handing over the validated assets and runbooks to the Change Management (E) and Hypercare (F) teams.

## Slide 39: Workstream D – Information Request List Data and access needed to rationalize and migrate legacy analytics
To effectively rationalize and migrate the vast library of legacy analytics, we need comprehensive data and access from the teams who manage and use these assets today.
Category | Specific Request | Required From
1. Foundational Inputs | Governed and conformed Silver domain tables. (Critical Blocker) Confirmed SPL-to-SQL translation logic and query performance guidelines from Workstream A. | Workstream C & A
2. Legacy Analytics Exports | Complete exports of all 11,199 in-scope objects from Splunk ES, Splunk Core, and AIOps. Data on query/dashboard ownership, usage frequency, and last-run dates. Documentation on any downstream systems that consume the output of these legacy analytics. | Splunk and AIOps Engineering Teams
3. Stakeholder & User Input | A list of power users and SMEs from the SOC and Observability teams to assist in prioritization and validation. A streamlined process for UAT and final sign-off on migrated analytics. | Business Analytics & End-User Teams
4. Technical Environment Access | Dedicated, isolated non-production workspaces in Databricks for the migration team to conduct development and testing. Access to the AI Transpilation Factory tooling and environments. | CVS Platform Team

## Slide 40: Workstream D – Proposed Meetings Cadence built around the tiered migration backlog
The meeting cadence for Workstream D is structured around a tiered migration backlog, ensuring a steady flow of delivery from rationalization through to user acceptance.
Meeting | Cadence | Purpose & Key Attendees
Month 1: October 2026 – Rationalization & Tier 1 Planning |  | 
Analytics Rationalization & Prioritization Board | Weekly | Review analytics usage data and prioritize the migration backlog into Tiers 1, 2, and 3. Attendees: Workstream D leads and CVS SOC/Observability team leads.
AI Transpiler Factory Sync | Weekly | Technical sync to manage the AI-assisted conversion pipeline, review transpilation accuracy, and refine the process. Attendees: KPMG migration engineers.
Month 2: November 2026 – Tier 1 Migration & Validation Sprints |  | 
Migration Sprint Planning & Review | Bi-Weekly | Agile ceremonies to plan the migration of a specific batch of queries/dashboards for the upcoming sprint. Attendees: Workstream D delivery pods.
User Acceptance Testing (UAT) Workshop | Bi-Weekly | Hands-on validation and sign-off sessions where end-users test the newly migrated dashboards and alerts in Databricks. Attendees: Workstream D engineers and nominated CVS power users.

## Slide 41: Workstream 0

## Slide 42: Workstream 0 – Project Management Support (1/2) Project Management – From the SOW and other planning documents
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx
Milestone
Description: Project Plan & Project Structure
Timing:
Deliverables:
Project Charter and Governance Framework (PPT/DOC)
Integrated Project Plan and Milestone Schedule (PPT/XLS)
Description: Weekly Status Reporting (recurring)
Timing:
Deliverables:
Recurring documents throughout the engagement:
Weekly Status Reports and Executive Steering Materials (PPT)
RAID Log and Decision Log (XLS)
KPI/Value Management Dashboard or tracker (PPT/XLS)
0.1
0.2
Governance, delivery management, status reporting, RAID management and value management.
Support management delivery of the project against schedule, budget, and to the required quality standards through governance, integrated planning and stakeholder alignment.
Scope
Objective
Key Activities
  Establish Governance & Reporting: Define project roles and responsibilities, meeting cadences, and reporting templates to encourage clear communication and decision-making
  Manage Risks, Issues, and Dependencies: Proactively identify, track, and mitigate project risks, issues, and inter-workstream dependencies to prevent delays
  Value Management: Track CVS-specified key performance indicators (KPIs)/metrics and provide regular status reports to stakeholders. Metrics include Data Parity, and Query Conversion Rate
  Manage Stakeholder Communications: Develop and execute a communications plan to assist CVS keep all stakeholders informed of project progress, decisions, and impacts.
  Kickoff Workshop: Align stakeholders on scope, objectives, and delivery plan
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27
Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27

## Slide 43: Workstream 0 – Project Management Support (2/2) Project Management – Planning
Key “Do Now” activities | Establish Governance Rhythms & Communication Plans: Draft the initial Project Charter and Governance Framework . This includes outlining meeting cadences, reporting templates, and defining project roles and responsibilities to ensure clear communication and decision-making on Day 1 Reconcile Project Plans: Resolve the current planning misalignment between Peter's plan and the KPMG plan for the bronze-layer workstream Set Up Risk, Issue, and Dependency Tracking: Create the initial RAID (Risks, Issues, Assumptions, and Dependencies) Log and Decision Log . This involves mapping cross-workstream dependencies, such as tracking Azure networking approvals, CVS security clearings, and pod delivery velocities Coordinate the Microsoft ECIF Funding Path: Align on the three-party commercial milestones and coordinate the upcoming planning session/funding discussions with Microsoft and CVS procurement stakeholders Confirm Resource Allocation & Staffing Readiness: Finalize the staffing plan with resource management for onshore/offshore roles to prevent pre-allocated team members from being reassigned due to SOW delays Prepare Team Onboarding Infrastructure: Initiate the creation of a centralized onboarding kit or knowledge repository to quickly ramp up incoming delivery pods once the SOW is finalized
Upstream Prerequisites | Commercial Authorization: Formal execution of the tri-party agreement / SOW and Microsoft ECIF/ESIF funding sign-off Architecture Assessment: Lovelytics current-state assessment findings (via Amit Gonsalves) to resolve baseline infrastructure and IAM gaps CVS Technical Inputs: Adam Plotzker’s architecture spreadsheet and stakeholder approval of the 26-table ODCS standard
Downstream Workstream Hand-offs | To Technical Pods (WS-B/C/D): Sprint work packages, prioritized backlogs, unblocked environmental credentials, and cross-workstream coordination To Executive Sponsors (CVS/Microsoft): Bi-weekly executive progress dashboards, budget burn reporting, and milestone acceptance packages To Hypercare & Operations (WS-F): Baselined operational runbooks, resolved defect logs, and formal governance transition artifacts
Epic | PMO Governance, Reporting & Steering Cadence | Integrated RAID & Financial Governance | Welcome Season & Change Freeze Governance | Agile Tooling & Jira WBS Ingestion
Features | 1.1: Executive Steering & Tactical Cadence Execution 1.2: Microsoft ECIF Co-Funding & Milestone Management | 2.1: Multi-Workstream Dependency & RAID Framework Integration 2.2: Resource Staffing & Blended Rate Financial Tracking | 3.1: Change Freeze Operational Playbook & Sandbox Boundaries 3.2: Foundational Day 1 Review Gate Q1/Q2 | 4.1: Jira WBS & Epic-to-Task Taxonomy Construction 4.2: Multi-Tier Modernization Priority Matrix
Source: Current KPMG planning, subject to change

## Slide 44: Workstream E

## Slide 45: Workstream E – Organizational Change and Adoption (1/2) Change management – From the SOW and other planning documents
Scope
Support adoption of Databricks platform through stakeholder alignment, training, communication planning, and a structured migration playbook. Provide Operational process documentation and runbooks to enable the CVS Health Operations team to effectively manage and maintain the environment based on the architecture and processes as designed.
Objective
Enable the successful migration and adoption of Databricks for CVS users by preparing stakeholders, training Power Users, establishing support networks to drive adoption.
Key Activities
  Align Strategy & Personas: Map existing legacy analytics platform use cases (SPL, dashboards) to Databricks SQL & Notebooks. Segment prioritized users into targeted personas (e.g., Novice, Security Ops, Data Scientist)
  Targeted Communications: Assist CVS launch persona-specific "What's in it for me?" campaigns (highlighting faster queries, ML capabilities). Showcase pilot success stories of complex Splunk-to-Databricks migrations
  “Train the Power User” model: Provide trainings to identified “Power Users” so they are enabled to teach courses to their colleagues and drive adoption
  Center of Excellence (CoE): Establish a central hub for ongoing support, training curriculum, office hours, and leading-practice repositories
  Adoption Planning: Design adoption plan to enable Power Users to support the progressive transition of user base from Splunk to Databricks including cutover plan
  Organizational Change Management scope discussion needed
Milestone
Description: Communication Plan
Timing: Sep 2026 – Dec 2026
Deliverables:
Organizational Impact Assessment (PPT) summarizing activities performed
Stakeholder and Persona Analysis (XLS/PPT)
Change Strategy and Rollout Blueprint (PPT)
Communications Plan and Draft Communications Content (XLS/DOC/PPT)
Learning Strategy and Training Materials (PPT/DOC)
Description: Tier 1 Power User Migration
Timing: Oct 2026 – May 2027
Deliverables:
Legacy analytics platform-to-Databricks Cheat Sheets and Notebook Templates (DOC/DBX) for Tier 1 use cases
Databricks Power User Program Materials (PPT/DOC) for Tier 1 users
Description: Tier 2 Power User Migration
Timing: Mar 2027 – Jul 2027
Deliverables:
Legacy analytics platform-to-Databricks Cheat Sheets and Notebook Templates (DOC/DBX) for Tier 2 use cases
Databricks Power User Program Materials (PPT/DOC) for Tier 2 users
Description: Tier 3 Power User Migration
Timing: May 2027 – Oct 2027
Deliverables:
Legacy analytics platform-to-Databricks Cheat Sheets and Notebook Templates (DOC/DBX) for Tier 3 use cases
Databricks Power User Program Materials (PPT/DOC) for Tier 3 users
CoE Operating Model and Adoption Plan (PPT/XLS)
E.2
E.4
E.1
E.3
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx

## Slide 46: Workstream E – Organizational Change and Adoption (2/2) Change management – Planning
Notional, to update
Source: Current KPMG planning, subject to change
Key “Do Now” activities | Establish Master Project Structure Formulate Staffing & Onboarding Requests Identify Target User Groups & Channels Outline Training Approach Strategy
Upstream Prerequisites | Living Pilot & Workspace Assets (from A): Architecture validation outcomes, role-to-Unity-Catalog access mapping frameworks, and reference schemas to structure the landing content. Query Performance Guidelines (from D): Confirmed Splunk and AIOps scope boundaries and translation logic to write accurate training guides User Nomination Lock: Delivery from CVS of nominated Power Users (minimum of 5 from each functional business unit) with dedicated, pre-cleared calendar time for training
Downstream Workstream Hand-offs | To Workstream 0 (PMO): Weekly adoption telemetry, training completion metrics, change strategy updates, and risk/issue tracking (especially regarding resource constraints or user resistance) To Workstream C (Pipeline Enablement): Business requirements gathered from user persona analysis to build targeted Gold/self-service workspace environments and configure Databricks Genie To Workstream F (Hypercare): Hand-off of the trained "Databricks Champions" network to act as first-line floor support during cutover, along with a validated CoE (Center of Excellence) operating model
Epic | Strategy, Alignment & Impact Assessment | Communications & Campaigns | Power User Enablement & Champions Program | Scale Adoption, Support, and Center of Excellence
Features | 1.1: Persona Mapping 1.2: Organizational Impact & Stakeholder Analysis | 2.1: Target Communication Strategy 2.2: Launch Campaign | 3.1: "Train the Trainer" Program 3.2: Legacy-to-Databricks Translation Aids | 4.1: Establish Center of Excellence (CoE) 4.2: End-User Rollout & Support

## Slide 47: Workstream F

## Slide 48: Workstream F – Hypercare and Operational Handoff (1/2) Transition – From the SOW and other planning documents
Source: CVS_Databricks_SOW_Draft_v5 JAS_CVS_REDLINE, CVS Databricks Staffing Model_V4.xlsx
Description: Cutover Support
Timing:
Deliverables:
Hypercare Plan and War Room Operating Model (PPT/DOC)
Hypercare Issue Log and Resolution Tracker (XLS)
Performance Tuning Summary and Recommendations (PPT/DOC)
Scope
Provide post go-live stabilization, incident triage, performance tuning, knowledge transfer and formal handoff support.
Objective
Coordinate transition post go-live by rapidly resolving issues, stabilizing the platform and executing a structured handoff to CVS BAU operations.
Key Activities
  Establish War Room: Set up a command center with daily stand-ups for rapid issue triage and escalation
  Intensive Incident Management: Provide monitoring and rapid response for pipeline, platform and data quality issues
  End-User Support: Act as the first point of contact for user support, providing hands-on assistance to resolve issues
  Performance Tuning: Monitor platform performance under production loads and implement tuning to meet performance benchmarks
  Knowledge Transfer (KT): Document all resolutions in a knowledge base and conduct focused transfer sessions to enable the BAU team
  Formal Handoff: Execute the handover process with a final system stability review to secure formal sign-off
Milestone
Description: Transition & Handoff
Timing: Oct 2027
Deliverables:
    Operational Runbooks and Knowledge Base Content (DOC)
    Knowledge Transfer Materials and Attendance Records (PPT/XLS)
    Service Transition Checklist and Handoff Signoff Document (DOC)
F.1
F.2
Sep26 | Oct26 | Nov26 | Dec26 | Jan27 | Feb27 | Mar27 | Apr27 | May27 | Jun27 | Jul27 | Aug27 | Sep27 | Oct27
Sep26 | Oct26 | Nov26 | Dec26 | Jan27 | Feb27 | Mar27 | Apr27 | May27 | Jun27 | Jul27 | Aug27 | Sep27 | Oct27

## Slide 49: Workstream F – Hypercare and Operational Handoff (2/2) Transition – Planning
Notional, to update
Source: Current KPMG planning, subject to change
Key “Do Now” activities | WBS and Sprint Planning: Create the Work Breakdown Structure (WBS), prioritization matrices, and Agile Sprint plans mapped against dependencies Staffing and Role Finalization: Reconcile and lock in technical resource allocation, aligning KPMG and Scicom delivery roles Provisional VDI Access Requests: Submit provisional VDI requests for resources by mid-October to preempt the typical 2-to-3-week administrative onboarding bottleneck BAU Resource Identification: Formally identify and align the CVS BAU support team members who will participate in the transition | 
Upstream Prerequisites | Platform Readiness (Workstream A): Complete firewall clearances, network port openings, Azure subscription provisioning, and ExpressRoute bandwidth validation to support high volume data flows Bronze Data Flow (Workstream B2): Fully establish Autoloader + Event Grid configurations and Cribl routing pathways to ensure all Splunk indexes are flowing into Bronze Delta tables Silver & Gold Curation (Workstream C): Build, normalize, and secure 9 Silver Domains (90–180 tables) and establish 12 Gold analytical products with business-accepted KPI logic Queries & Alerts Migration (Workstream D): Complete the translation and validation of the 11,199 scoped legacy observability objects (10,503 Splunk Core/ES/AIOps queries and 696 dashboards) Power User Enablement (Workstream E): Identify and train "Power Users" (at least 5 per functional area) to act as the first-line transition support network | 
Downstream Workstream Hand-offs | To CVS BAU Operations Team: Deliver operational runbooks, transition checklists, and knowledge base documentation Hand over final performance-tuning metrics and stabilization summary reports Conduct structured knowledge transfer (KT) sessions and secure formal handoff sign-offs | To CVS Data Governance & Platform Teams: Transition ownership of the unified metadata registries, lineage mappings, and data contract compliance models inside Unity Catalog Transfer active performance monitoring dashboards and pipeline execution alerts in Azure Databricks
Epic | Cutover Support & Platform Stabilization | Transition & Operational Handoff
Features | War Room Mobilization Intensive Incident Management End-User Triage Support Performance Tuning | Knowledge Base Documentation Targeted Training Sessions Handoff Verification

## Slide 50: Welcome Season Change Freeze Planning Mitigating Timeline Risks & Securing the Critical Path
Welcome Season Change Freeze: Operational Guardrails
Constraint: CVS enforces a firm-wide Welcome Season Change Freeze beginning in Dec through January
What It Means: No new code deployments, schema changes, or infrastructure modifications can be made to the Production environment during this blackout period
Opportunity: Development and validation work can and will continue in the non-production / sandbox environments. The change freeze does not mean a complete stop to development
Critical Dependency - Landing 5 Key Datasets by Dec 1: To ensure the team can work productively during the blackout, we should ingest live telemetry streams before the freeze
Recommended Action: We recommend that CVS sponsors authorize the prioritization of the 5 critical datasets with the internal data-owner teams. In parallel, CVS must issue provisional VDI access requests by mid-October to ensure the delivery team is operational on Dec 1
Potential Challenges:
Treating Dec as "Lost": Continue progress during the blackout period. By securing early development sandbox data, we can complete 100% of pipeline mapping and dry-run validation ahead of January production release
Late Sandbox Provisioning: Sandbox environments are occasionally included in change-freeze restrictions. Confirm with CVS that development sandboxes are exempt from freeze
“Known Unknowns”: Identify activities that must be completed before the change freeze to avoid critical delays
Dependency | Required Action | Target Date | Impact
Land 5 Key Datasets | Ingest and validate the five critical security and observability datasets directly into Databricks. | December 1, 2026 | If this date is missed, the team may not have live telemetry data for validation, which will impact the start of Workstream B development.
Notes: Talking Points:
The Critical Dependency: "As outlined on slide 9, our ability to work effectively during the November-January change freeze is entirely dependent on ingesting the five key telemetry datasets by Dec 1. This is not a 'nice to have'; it's a 'must-have'."
The Cost of Inaction: "If we miss this date, Workstream B (Ingestion) will be delayed by at least a quarter. This will have a cascading effect on all subsequent workstreams, delaying the entire project and postponing the delivery of value to CVS."
The Path to Success: "To prevent this, we need two things: formal ratification of the SOW this week, and authorization for provisional VDI access by mid-October. This gives us a clear, albeit narrow, window to succeed."

## Slide 51: SOW & Role Mapping Review Commercial Alignment, Resource Optimization, and Plan Reconciliation
Overview:
Document Progression: Statement of Work (SOW) successfully progressed to Version 6, incorporating updates and feedback from teams in last several days
Role Mappings & Estimates: Master estimation spreadsheet serves as the single source of truth for role definitions, capacity models, and resource efforts
Resource Allocation & Workstream Coverage: Completing a review to confirm operational coverage across all core workstreams
Recommended Action:
Leaders to finalize SOW and agree on decision to start at risk as soon as possible to avoid potential delays which may increase VDI/Onboarding/staffing bottlenecks, and potentially impact deadlines ahead of Dec 1 Welcome Season Change Freeze
Workstream / Focus Area | Key Roles Mapped (SOW) | Status
Workstream A: Foundation | Solution Architects, Security Specialists | Fully allocated; aligned to core deliverables
Workstream B: Ingestion | Data Engineers, PySpark Developers | Audit in progress to align KPMG & Scicom roles
Workstream C: Enablement | Agile PMO, Change Management Leads | Fully allocated; driving bottom-up planning

## Slide 52: ECIF & ESA Funding Maximization Aligning Technical Capacity Models with Strategic Funding Vehicles
Technical Baseline: Capacity & Consumption Estimates
Data Volume Baseline: The baseline capacity model is finalized at 300 Terabytes (TB) of observability and security telemetry
Incremental Buffer: An additional 10 TB has been modeled to accommodate expanding data pipeline requirements, bringing the active estimate to 310 TB
Calculations Single Source: All background consumption formulas, role mappings, and capacity assumptions are documented in the master spreadsheet transmitted on September 21
Commercial Strategy: Optimizing Funding Pools: We are executing a dual-track strategy to leverage Microsoft funding and maximize CVS’s Enterprise Agreement flexibility
Recommended Action:
Proposed Path Forward: Align ECIF calculation model with our 310 TB baseline to secure maximum external funding before the Dec 1 Change Freeze limits operational window
Potential Challenges:
ESA Allocation: Ensure the $10M ESA allotment is confirmed for the work, was noted that most of the broader $100M pool is already spoken for across CVS
Incremental Ingestion Overruns: Telemetry sources often experience volume spikes. Architecture teams should design ingestion throttles to prevent unexpected billing overruns
Funding Source | Project Allocation | Strategic Leverage/ Action
Microsoft ECIF | Baseline Estimate | Action: Naga Kalidindi to sync with Microsoft to clarify the calculation algorithm and request an upward adjustment to match SOW scope expansion.
CVS Microsoft ESA | $9.8M is earmarked from the ECIF | Action: Leverage ESA program flexibility to absorb incremental consumption and cover SOW role requirements if ECIF caps are reached