KPMG  ·  CVS HEALTH

Enterprise Observability and Security Data Foundation

Workstream A

Architecture Assessment, Use Case Validation & Remediation

Detailed Methodology

At a glance Assess architecture readiness across 7 core domains, prove the production pattern through one end-to-end Bronze → Silver → Gold pilot, and remediate prioritized gaps while producing a validated architecture baseline and handoff package that Workstreams B–E can build on without rework.

| Document | Detail |
| --- | --- |
| Program | Enterprise Observability & Security Data Foundation |
| Workstream | A — Architecture Assessment, Use Case Validation & Remediation |
| Supplements | SOW Section 2.3 (A1 / A2 / A3) |
| Timeline | 12 weeks (A1: Wks 1–6 · A2: Wks 7–10 · A3: Wks 4–12) |
| Scope | 7 assessment domains · 1 end-to-end pilot · prioritized remediation |
| Target Output | Validated architecture baseline + B–E handoff package |
| Prepared by | KPMG |

Contents

1.0  Approach Overview	4

2.0  A1 — Architecture Assessment Methodology	6

2.1  Seven Assessment Domains	6

2.2  Assessment Execution Process	6

2.3  Scoring Rubric	7

2.4  Domain-Specific Checklists	7

2.5  Gap Register Format	11

2.6  Multi-Workspace Scope	11

2.7  Lovelytics Coordination	12

3.0  A2 — Pilot Use Case Methodology	13

3.1  Pilot Selection Criteria	13

3.2  Pilot Scope Definition	13

3.3  Pilot Implementation Steps	14

3.4  Pilot Success Criteria	14

3.5  Pilot as Reference Pattern	14

4.0  A3 — Remediation Methodology	16

4.1  Prioritization Framework	16

4.2  Remediation Categories	16

4.3  Evidence Collection	17

4.4  Handoff to Downstream Workstreams	17

5.0  Deliverable Framework	18

5.1  Current-State Architecture Assessment Report	18

5.2  Security, Governance and FinOps Findings Register	18

5.3  Pilot Use Case Design and Implementation Evidence	18

5.4  Architecture Remediation Tracker	18

5.5  Day 1 Go-Live Architecture and Day 2 Roadmap	18

5.6  Workstream B–E Handoff Package	19

6.0  Stakeholder Engagement	20

6.1  Interview Schedule	20

6.2  Recurring Cadences	20

6.3  Access Requirements (Critical Path)	20

7.0  Delivery Cadence	22

7.1  Week-by-Week Execution	22

7.2  Key Milestones	22

8.0  Alignment with SOW Scope and Deliverables	24

1.0  Approach Overview

This document describes the detailed methodology KPMG will employ to assess the current Azure/Cribl/Databricks architecture, validate it through an end-to-end pilot use case, and remediate prioritized gaps before downstream workstreams begin at-scale delivery. It supplements SOW Section 2.3 (Workstream A1/A2/A3) by providing the specific assessment framework, scoring methodology, pilot selection criteria, remediation prioritization approach, and deliverable structure.

The Problem The CVS Databricks environment has its foundations but is functionally immature. Strong governance/SDLC/Unity Catalog foundations were started, but there are no demonstrable or useable outputs (no production schemas, no validated tables, no queries, no reports). A key architect recently departed with limited knowledge transfer. The platform spans multiple Databricks workspaces across Azure and AWS, and a separate Lovelytics assessment is underway that may overlap WS-A scope.

The Objective Assess architecture readiness across 7 domains. Execute one end-to-end pilot (Bronze → Silver → Gold) proving the production pattern. Remediate prioritized gaps. Produce a validated architecture baseline and handoff package that downstream workstreams (B, C, D, E) can build on without rework.

Sub-Phases

| Phase | Duration | Focus |
| --- | --- | --- |
| A1 — Architecture Assessment | Weeks 1–6 | Structured assessment across 7 domains; gap register; recommendations |
| A2 — Use Case Validation (Pilot) | Weeks 7–10 | End-to-end pipeline build; performance test; demo |
| A3 — Architecture Remediation | Weeks 4–12 (overlaps A1/A2) | Prioritized gap resolution; evidence collection |

Relationship to Other Workstreams

- WS-A produces the validated architecture baseline that B1, B2, C, and D build upon

- WS-A’s pilot becomes the reference implementation pattern for WS-C pipeline templates

- WS-A’s security findings inform WS-C governance implementation (masking rules, RLS, classification)

- WS-A’s FinOps baseline informs WS-C DLT (and underlying Azure storage account) tiering decisions

- WS-A validates AIOps/ITSI scope for WS-D (determining what exists and what’s migrateable)

Companion Document The CVS Environment Walkthrough for Workstream A Architect provides detailed environment context, physical architecture, stakeholder map, and known risks. This methodology document focuses on HOW we execute the assessment, not what the environment looks like.

2.0  A1 — Architecture Assessment Methodology

2.1  Seven Assessment Domains

The architecture assessment is organized into 7 structured domains, each with a defined scope, interview guide, checklist, and scoring rubric:

| # | Domain | Key Topics | Primary CVS Stakeholders |
| --- | --- | --- | --- |
| 1 | Unity Catalog & Data Lifecycle | Taxonomy design, RBAC/ABAC design, Workspace isolation, Chargeback model and capability, retention policies | Platform Team, Raj/Amar |
| 2 | Security Architecture | Review of: threat model, Zero Trust controls validation, Data exfiltration prevention, Pipeline compliance checkpoints | Security SMEs, Chris Robinson |
| 3 | Encryption Posture | CMK at rest, TLS 1.3 in transit, Row-level encryption options, Key rotation. | Security SMEs, Platform Team |
| 4 | Data Protection & DR | Compute Regions, Recovery objectives (RPO/RTO), Redundancy, Cross-region failover, Backup strategy. | Platform Team, Infrastructure |
| 5 | Scalability & Resilience | 400 TB/day validation, data source validation, user size/scale (10k), Autoloader sizing, Compute scaling | Platform Team, Shivpratap Singh? |
| 6 | FinOps | Cost allocation, Cluster policies, Compute governance, Budget vs. actual, Chargeback model | FinOps team, Platform Team |
| 7 | CI/CD & DataOps | Git integration, Deployment pipeline, Promotion gates, Testing approach, Environment parity. | Platform Team, Engineering |

2.2  Assessment Execution Process

STEP 1

Input

STEP 2

Validation

1

INTERVIEW

• Structured interviews with CVS stakeholders

• Domain-specific interview guide prepared in advance

• Findings documented with evidence links

2

EVIDENCE COLLECTION

• Request documentation, configurations, screenshots, and exports

• Validate configuration against stated policies

• Identify gaps between standards and implementation

For each domain, the assessment follows a 4-step process:

STEP 3

Assessment

STEP 4

Action Plan

3

SCORING

• Score each item on R/Y/G enterprise standards

• Document rationale for each score

• Identify dependencies and downstream impacts

4

RECOMMENDATION

• Propose remediation for Yellow/Red items

• Estimate effort using S/M/L/XL sizing

• Set priority and assign owner: KPMG A3, CVS, SciCom, or Lovelytics Deferred

AI-Accelerated Discovery (CVS GenAI / KPMG Blaze):

Where access permits, KPMG Blaze accelerates Steps 1–2 by ingesting existing Splunk configurations, pipeline code, and infrastructure artifacts into its Knowledge Base:

- Code Summary: Automated decomposition of legacy ingestion pipelines and analytics logic into logical components — compresses discovery across large, undocumented estates and surfaces dead code, duplicated detections, and rationalization candidates.

- Knowledge Graph: Visual dependency mapping across Splunk applications, indexes, sourcetypes, searches, dashboards, and knowledge objects — replaces weeks of manual architecture diagramming.

- Agentic Chat: Engineers query pipeline behavior and cross-component dependencies in natural language — shortens onboarding and reduces SME dependency during the assessment phase.

These capabilities reduce assessment timeline by accelerating evidence collection and gap identification without waiting on specialist availability.

Interactive Search Gap Assessment:

As part of the Scalability domain assessment, WS-A will evaluate whether CVS SOC teams' interactive investigation requirements (ad-hoc threat hunting, regex pattern discovery, real-time log search) exceed what Databricks SQL capabilities can deliver at acceptable latencies. If confirmed, the assessment will recommend an Elasticsearch/OpenSearch sidecar index architecture as a future-phase enhancement to meet any analytics gaps (see WS-D Section 15.1 for architectural pattern).

2.3  Scoring Rubric

| Score | Meaning | Action Required |
| --- | --- | --- |
| Green | Meets enterprise production standards; no remediation needed | Document as validated; no action |
| Yellow | Partially meets standards; functional but has gaps or risks | Remediate during A3 or accept risk with documentation |
| Red | Does not meet standards; blocks production readiness or creates unacceptable risk | Must remediate before downstream workstreams can proceed |

2.4  Domain-Specific Checklists

Domain 1 — Unity Catalog & Data Lifecycle

| Assessment Item | Evidence Required | Scoring Criteria |
| --- | --- | --- |
| Catalog taxonomy defined and documented | Catalog list, naming conventions | Green: documented + follows pattern; Red: no documentation or ad-hoc naming |
| RBAC/ABAC policies configured | Access policies, group memberships | Green: role-based, least privilege; Red: overly permissive or missing |
| Workspace isolation by data classification | Workspace config, network rules | Green: PHI isolated; Red: no classification boundary |
| Row/column-level security implemented | Tag configuration, filter rules | Green: configured per data class; Yellow: partial; Red: none |
| Data retention policies configured | Lifecycle policies, WORM config | Green: policies active; Yellow: defined not enforced; Red: missing |
| Chargeback model defined | Cost allocation tags, workspace billing | Green: per-team allocation; Yellow: partial tagging; Red: no attribution |
| Lineage tracking enabled | Unity Catalog lineage views | Green: automatic lineage visible; Red: lineage not configured |

Domain 2 — Security Architecture

| Assessment Item | Evidence Required | Scoring Criteria |
| --- | --- | --- |
| Threat model documented | Threat model document | Green: current and reviewed; Red: missing |
| Zero Trust controls implemented | Network config, identity verification | Green: no implicit trust; Yellow: partial; Red: perimeter-only |
| Data exfiltration controls | Egress rules, DLP policies | Green: monitored + restricted; Red: unrestricted egress |
| Pipeline compliance checkpoints | Pipeline audit logs, validation steps | Green: automated checks; Yellow: manual; Red: none |
| Platform attestation | Security review evidence | Green: reviewed + attested; Red: no review |
| PHI masking completeness | Masking rules, test evidence | Green: all PHI fields masked; Yellow: partial; Red: gaps identified |
| Multi-tenant isolation | Workspace boundaries, credential isolation | Green: fully isolated; Red: shared credentials or cross-workspace access (no partial Yellow) |

Domain 3 — Encryption Posture

| Assessment Item | Evidence Required | Scoring Criteria |
| --- | --- | --- |
| Customer-managed keys (CMK) for data at rest | Key Vault configuration, ADLS encryption settings | Green: CMK active with rotation policy; Yellow: platform-managed keys; Red: no encryption or unmanaged keys |
| TLS 1.3 enforced for all data in transit | Network policies, TLS configuration | Green: TLS 1.3 enforced; Yellow: TLS 1.2 minimum with 1.3 preferred; Red: TLS 1.1 or below permitted |
| Row-level encryption options assessed | Encryption design, field sensitivity mapping, masking/encryption rules | Green: options assessed and applied where required; Yellow: assessed but not fully implemented; Red: not assessed |
| Key rotation policy defined and automated | Key Vault rotation policies, audit logs | Green: automated rotation ≤90 days; Yellow: manual rotation with schedule; Red: no rotation |

Domain 4 — Data Protection & Disaster Recovery

| Assessment Item | Evidence Required | Scoring Criteria |
| --- | --- | --- |
| Compute regions documented | Workspace region inventory, cloud deployment maps | Green: all regions documented and justified; Yellow: partial inventory; Red: unknown regional footprint |
| RPO/RTO defined per data tier | DR policy document | Green: documented and tested per tier; Red: undefined |
| Redundancy implemented for critical components | Architecture diagrams, HA configuration, service redundancy evidence | Green: redundancy active for critical path; Yellow: partial; Red: single points of failure |
| Cross-region failover configured | Failover runbooks, ADLS replication settings, Databricks workspace config | Green: tested failover; Yellow: configured but untested; Red: no failover pattern |
| Backup strategy defined and validated | Backup schedules, restore test evidence, retention configuration | Green: backup and restore tested; Yellow: backup exists but restore untested; Red: no backup strategy |

Domain 5 — Scalability & Resilience

| Assessment Item | Evidence Required | Scoring Criteria |
| --- | --- | --- |
| Autoloader validated at target volume | Load test results | Green: 400 TB/day sustained; Yellow: partial test; Red: untested |
| Event Grid notification latency | Monitoring data | Green: <30s notification; Yellow: 30s–2min; Red: >2min or unreliable |
| Compute auto-scaling configured | Cluster policies, scaling rules | Green: auto-scale with limits; Red: fixed clusters |
| Storage scaling verified | ADLS metrics, throughput limits | Green: proven at scale; Red: theoretical only |
| Concurrent user capacity | Query concurrency test | Green: 10k user simulated; Yellow: limited test; Red: untested |
| +50% burst headroom validated | Burst test results | Green: sustained burst without degradation; Red: untested |
| Recovery from failure (resilience) | Failure injection test | Green: automatic recovery <10 min; Red: manual intervention required |

Domain 6 — FinOps

| Assessment Item | Evidence Required | Scoring Criteria |
| --- | --- | --- |
| Cost allocation by workspace/team | Tagging policies, cost reports | Green: per-team/workspace attribution active; Yellow: partial tagging; Red: no cost attribution |
| Cluster policies enforcing compute governance | Policy definitions, max DBU limits | Green: policies active; Yellow: policies exist but unenforced; Red: no governance |
| Compute governance standards documented | Compute standards, approved instance types, auto-termination settings | Green: standards documented and enforced; Yellow: documented only; Red: ad hoc compute usage |
| Budget vs. actual tracked | Budget reports, variance dashboards, alert thresholds | Green: active budget tracking with alerts; Yellow: periodic manual review; Red: no budget tracking |
| Chargeback model defined | Cost allocation rules, chargeback reports, stakeholder approval | Green: chargeback implemented; Yellow: showback only; Red: no financial accountability model |

Domain 7 — CI/CD & DataOps

| Assessment Item | Evidence Required | Scoring Criteria |
| --- | --- | --- |
| Git integration configured | Repos configuration, workspace settings | Green: all notebooks/pipelines version-controlled; Yellow: partial; Red: no Git integration |
| Deployment pipeline (Dev→QA→Prod) | CI/CD configuration (ADO/GitHub Actions) | Green: automated promotion with gates; Yellow: manual promotion with process; Red: no separation of environments |
| Promotion gates defined and enforced | Approval workflow, quality gates, release evidence | Green: automated gates enforced; Yellow: manual gates; Red: no promotion controls |
| Testing approach defined | Unit tests, integration tests, data quality tests, test results | Green: automated tests in pipeline; Yellow: manual or partial tests; Red: no testing approach |
| Environment parity maintained | Environment configuration comparison, infrastructure-as-code, workspace settings | Green: environments aligned through code; Yellow: documented differences; Red: inconsistent environments |

2.5  Gap Register Format

All findings are recorded in a structured Gap Register:

| Field | Description |
| --- | --- |
| Gap ID | Unique identifier (e.g., SEC-003) |
| Domain | Assessment domain (1–7) |
| Item | Specific checklist item |
| Current State | What exists today |
| Target State | What production readiness requires |
| Score | Red / Yellow / Green |
| Impact | What breaks if not remediated (downstream workstream, SLA, compliance) |
| Remediation | Proposed fix |
| Effort | T-shirt size (S/M/L/XL) |
| Priority | Must-fix-before-freeze / Day 2 roadmap |
| Owner | KPMG (A3) / CVS / SciCom / Deferred |
| Status | Open / In Progress / Resolved / Accepted |

2.6  Multi-Workspace Scope

Discussion on (Jul 8) clarified that the effort spans multiple Databricks workspaces across Azure and AWS. The assessment will:

- Inventory all workspaces (reported as ~201)

- Classify each workspace by purpose, data classification, and owner

- Assess governance consistency across workspaces

- Identify workspaces requiring security hardening or normalization

- Recommend overall workspace strategy, consolidation or isolation adjustments

2.7  Lovelytics Coordination

A Lovelytics assessment is underway that may overlap WS-A scope. KPMG will:

- Request Lovelytics assessment scope and timeline in Week 1

- Map overlap areas (security domains 2, 3 likely overlap)

- Agree boundary: Lovelytics findings feed A3 remediation rather than duplicating assessment

- Consume Lovelytics outputs as inputs to KPMG’s gap register

- Document any remaining gaps not covered by Lovelytics

3.0  A2 — Pilot Use Case Methodology

3.1  Pilot Selection Criteria

The pilot use case should satisfy all of the following:

| Criterion | Requirement | Rationale |
| --- | --- | --- |
| Representative complexity | Spans Bronze → Silver → Gold with at least one enrichment join | Proves the full Medallion pattern, not just ingestion |
| Production-representative volume | Source generates meaningful volume (>1 TB/day) | Validates performance at realistic scale |
| Persona coverage | At least 2 user personas consume the output | Validates RBAC, access patterns, and usability |
| Data availability | Source data already landing in Bronze (or can be made available quickly) | Minimizes dependency on B2 timeline |
| Business visibility | Stakeholders care about the result; executive demo potential | Builds confidence and momentum |
| Schema diversity | Includes structured + semi-structured data | Validates parsing and normalization patterns |
| Security relevance | Involves PHI/PII masking or row-level security | Validates governance implementation |

Likely candidates K8s/CRM application telemetry (high volume, persona diversity, K8s metadata complexity) or Network Security (multi-vendor consolidation, OCSF normalization, SOC visibility).

3.2  Pilot Scope Definition

Once selected, the pilot is formally scoped:

| Element | Definition |
| --- | --- |
| Source family | Specific source family from B1 taxonomy (e.g., “CRM Kubernetes” or “Network Security — Palo Alto”) |
| Bronze table | Which existing or net-new Bronze table(s) the pilot reads from |
| Silver table(s) | Target Silver schema with normalization applied |
| Gold output | Dashboard, Genie semantic model, or analytical query set |
| Success criteria | Measurable outcomes (latency, accuracy, user validation) |
| Personas | Who will consume and validate |
| RBAC validation | Prove that different personas see different data based on Unity Catalog policies |
| Stakeholders | CVS approver(s) for scope and acceptance |

3.3  Pilot Implementation Steps

| Step | Activities | Duration | Output |
| --- | --- | --- | --- |
| 1. Scope & Prepare | Select use case; define success criteria; provision compute; confirm data availability | Week 7 | Pilot design document; environment provisioned |
| 2. Ingest & Engineer | Build DLT pipeline (Bronze → Silver); implement masking; apply quality expectations | Week 8 | Working DLT pipeline; Silver table populated |
| 3. Model & Analyze | Build Gold aggregation; create dashboard or Genie model; apply enrichment (CMDB join) | Week 9 | Gold product; working analytics |
| 4. Performance Test | Validate at production-representative throughput and concurrency; stress test | Week 9–10 | Performance test results |
| 5. Validate & Showcase | QA with CVS stakeholders; document learnings; deliver executive demo | Week 10 | Demo delivered; learnings documented |

3.4  Pilot Success Criteria

| Metric | Target |
| --- | --- |
| End-to-end latency (source → Gold) | < 15 minutes for warm tier; < 5 minutes for hot |
| Data quality pass rate | > 98% (DLT expectations) |
| Schema accuracy | Silver output matches contracted schema (B1 contract) |
| RBAC validated | Different personas confirmed seeing appropriate data |
| PHI masking confirmed | No PHI visible in Silver/Gold without authorized role |
| Concurrency | 10+ simultaneous queries without degradation |
| Stakeholder acceptance | CVS product owner signs off on output quality |

3.5  Pilot as Reference Pattern

The pilot is not a one-off demo — it becomes the reference implementation that WS-C uses to build all subsequent pipelines:

- DLT pipeline code becomes the first entry in the template library (WS-C Section 3)

- Silver schema becomes the first domain model (WS-C Section 4)

- Gold output becomes the first self-service example (WS-C Section 7)

- RBAC configuration becomes the governance pattern (WS-C Section 5)

- Performance results set the baseline for SLA expectations (WS-B2 Section 7)

4.0  A3 — Remediation Methodology

4.1  Prioritization Framework

Not all Red/Yellow gaps can or should be remediated within the WS-A timeline. Prioritization uses a 2×2 matrix:

LOW EFFORT

HIGH EFFORT

LOW IMPACT

HIGH IMPACT

MUST FIX

Before freeze

• High operational or compliance exposure

• Clear blocker to readiness or go-live

• Remediation is achievable within WS-A timeline

PLAN & SEQUENCE

Day 2 roadmap

• High-value gap with larger remediation effort

• Requires dependency planning or funding

• Sequence based on critical path and risk reduction

QUICK WIN

Fix now where practical

• Low effort cleanup or configuration update

• Evidence, documentation, or workflow improvement

• Can be closed quickly without major dependency

ACCEPT / DEFER

Risk acceptance or next phase

• Lower delivery impact relative to effort

• Requires explicit owner and acceptance decision

• Revisit after freeze or as part of future roadmap

| Quadrant | Action | Timeline |
| --- | --- | --- |
| Must Fix (high impact, low effort) | Remediate during A3; blocks downstream work | Weeks 4–12 |
| Quick Win (low impact, low effort) | Fix opportunistically during A3 | Weeks 4–12 |
| Plan & Sequence (high impact, high effort) | Include in Day 2 roadmap; may require Change Order | Post-engagement |
| Accept / Defer (low impact, high effort) | Document risk; obtain CVS risk acceptance | Deferred |

4.2  Remediation Categories

| Category | Examples | Typical Effort |
| --- | --- | --- |
| Security controls | Zero Trust implementation, exfiltration prevention, MFA enforcement | M–L |
| Autoloader sizing | Compute scaling, cluster policies, Event Grid throughput | S–M |
| PHI masking rules | Regex patterns, NER models, field identification | M |
| Unity Catalog ACLs | Policy configuration, group management, tag enforcement | S–M |
| Networking | Static NAT validation, private endpoint configuration, firewall rules | M–L |
| CI/CD maturity | Git integration, deployment pipelines, promotion gates | M–L |
| Workspace normalization | Consolidation, naming standards, cross-workspace governance | L |

4.3  Evidence Collection

For each completed remediation:

| Evidence Element | Purpose |
| --- | --- |
| Before state | Screenshot/config showing the gap |
| Remediation action | What was changed (code, config, policy) |
| After state | Screenshot/config showing resolution |
| Validation test | Test proving the fix works |
| Approval | CVS sign-off on remediation (where applicable) |

4.4  Handoff to Downstream Workstreams

A3 produces a Workstream B–E Handoff Package containing:

- Validated architecture diagram (current state + remediated state)

- Remaining gap register (items not remediated; deferred or Day 2)

- Architecture decisions made during A1/A2/A3 that constrain downstream design

- Pilot reference implementation (code, config, patterns) for WS-C to inherit

- Security controls validated (for WS-C governance implementation)

- FinOps baseline (for WS-C DLT tiering decisions)

- Lovelytics findings summary (for awareness across all workstreams)

5.0  Deliverable Framework

5.1  Current-State Architecture Assessment Report

| Section | Content |
| --- | --- |
| Executive Summary | Overall readiness score; top 5 findings; recommended path forward |
| Per-Domain Assessment | For each of 7 domains: current state, findings, scores, recommendations |
| Gap Register | Complete register of all Red/Yellow items with prioritization |
| Multi-Workspace Inventory | Workspace catalog with classification and governance status |
| Lovelytics Integration | How KPMG findings align with/complement Lovelytics assessment |

5.2  Security, Governance and FinOps Findings Register

- Structured spreadsheet (XLS) with all scored items across domains 1, 2, 3, 4, 6 (domains 5 and 7, Scalability and CI/CD, are more operational/engineering than governance/security)

- Filterable by score, domain, priority, owner

- Linked to remediation tracker

5.3  Pilot Use Case Design and Implementation Evidence

- Pilot scope document (use case, personas, success criteria)

- Pipeline code (DLT notebook + configuration)

- Silver schema documentation

- Gold output (dashboard or Genie model)

- Performance test results

- Stakeholder validation evidence

5.4  Architecture Remediation Tracker

- Linked to Gap Register

- Status tracking per remediation item

- Before/after evidence per completed item

- Risk acceptance documentation for deferred items

5.5  Day 1 Go-Live Architecture and Day 2 Roadmap

| Section | Content |
| --- | --- |
| Day 1 Architecture | What’s production-ready after A3 remediation; validated target-state diagram |
| Day 2 Roadmap | Prioritized backlog of items requiring longer-term effort; sequencing recommendations |
| Decision Log | Architecture decisions made during WS-A with rationale |
| Constraints | Items that constrain downstream design (e.g., workspace boundaries, networking limitations) |

5.6  Workstream B–E Handoff Package

- Summary of architecture decisions affecting each downstream workstream

- Per-workstream: “what you can assume is validated” + “what you need to be aware of”

- Reference implementation artifacts (code, configs, patterns)

- Open items requiring downstream attention

6.0  Stakeholder Engagement

6.1  Interview Schedule

| Week | Domain(s) | CVS Stakeholders | Format |
| --- | --- | --- | --- |
| 1 | Unity Catalog, CI/CD | Raj/Amar, Platform Team | 2-hour workshop |
| 2 | Security, Encryption | Security SMEs, Chris Robinson | 2-hour workshop |
| 2 | Data Protection, DR | Platform Team, Infrastructure | 1.5-hour interview |
| 3 | Scalability, Resilience | Shivpratap Singh, Matthew Filippone, Platform Team | 2-hour workshop |
| 3 | FinOps | FinOps team, Platform Team | 1.5-hour interview |
| 4 | Lovelytics coordination | Lovelytics team (if accessible) | 1-hour alignment |
| 5 | Pilot scoping | Josh/Chris, product owners | 1-hour decision meeting |

6.2  Recurring Cadences

| Meeting | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| WS-A Stand-up | Daily | KPMG A team | Coordination, blockers |
| Assessment Progress | Weekly | KPMG + CVS Platform Team | Findings review, evidence requests |
| Pilot Check-in | Twice weekly (Weeks 7–10) | KPMG + CVS stakeholders | Pilot progress, blockers, demos |
| Executive Checkpoint | Bi-weekly | KPMG Lead + Josh/Chris | Assessment progress, key findings, decisions |
| Handoff Prep | Weeks 11–12 | KPMG A + B/C/D leads | Handoff content review |

6.3  Access Requirements (Critical Path)

| Access | Owner | Lead Time | Notes |
| --- | --- | --- | --- |
| Databricks workspace (all) | Raj/Amar (SciCom) | 1–2 weeks | Provisioning + security approval |
| Azure subscription visibility | CVS Platform Team | 1–2 weeks | Reader access for architecture review |
| Splunk access | CVS Splunk Team | 2–4 weeks | Requires security approval process |
| Unity Catalog admin view | CVS Platform Team | 1 week | Needed for taxonomy assessment |
| Network/firewall documentation | CVS Infrastructure | 1 week | Static NAT configs, private endpoints |
| Lovelytics findings | CVS Security / Lovelytics | TBD | May require NDA or coordination |

Risk Access approvals may require significant lead time. Assessment timeline depends on access being granted by Week 1–2. Delayed access = delayed assessment = compressed remediation window before November freeze.

7.0  Delivery Cadence

7.1  Week-by-Week Execution

| Week | Phase | Key Activities | Key Outputs |
| --- | --- | --- | --- |
| 1 | A1 | Environment access; inventory all workspaces; review documentation; prepare checklists; identify departed architect’s artifacts | Access confirmed; workspace inventory; checklist library |
| 2 | A1 | Security + Encryption interviews; begin evidence collection; engage Lovelytics | Domain 2+3 findings (draft); Lovelytics alignment |
| 3 | A1 | Scalability + FinOps interviews; Autoloader load testing; compute policy review | Domain 5+6 findings (draft); initial load test results |
| 4 | A1/A3 | Unity Catalog + CI/CD deep dive; complete gap register; begin prioritization | Complete gap register v1; priority recommendations |
| 5 | A1/A3 | Finalize assessment report; pilot use case selection; A3 remediation begins on Quick Wins | Assessment report (draft); pilot scope approved |
| 6 | A1/A3 | Assessment report reviewed with CVS; remediation in progress; pilot prep | Assessment report (final); pilot environment provisioned |
| 7 | A2 | Pilot: Scope & Prepare; DLT pipeline development begins | Pilot design doc; initial pipeline code |
| 8 | A2/A3 | Pilot: Ingest & Engineer; Silver table populated; remediation continues | Working Silver pipeline; remediation progress |
| 9 | A2/A3 | Pilot: Model & Analyze; Gold output created; performance testing begins | Gold product; performance test plan executed |
| 10 | A2/A3 | Pilot: Validate & Showcase; executive demo; performance results finalized | Demo delivered; performance report |
| 11 | A3 | Remediation finalization; evidence collection; Day 1/Day 2 roadmap | Remediation tracker (final); Day 1/Day 2 doc |
| 12 | Handoff | Handoff package assembly; B/C/D briefings; knowledge transfer | Handoff package delivered; WS-B/C/D briefed |

7.2  Key Milestones

| Milestone | Target Week | Gate |
| --- | --- | --- |
| Access granted (all environments) | Week 1–2 | Cannot assess without access |
| Gap register v1 complete | Week 4 | Assessment findings drive remediation prioritization |
| Assessment report delivered | Week 6 | CVS reviews and approves findings |
| Pilot scope approved | Week 5 | CVS signs off on use case selection |
| Pilot demo delivered | Week 10 | Executive visibility; validates architecture |
| Remediation complete (must-fix items) | Week 11 | Downstream workstreams unblocked |
| Handoff package delivered | Week 12 | B/C/D teams have validated baseline |

8.0  Alignment with SOW Scope and Deliverables

| SOW Deliverable | Methodology Section |
| --- | --- |
| Current-State Architecture Assessment Report | Sections 2 (Assessment) + 5.1 (Report structure) |
| Security, Governance and FinOps Findings Register | Section 2 (Domain checklists) + 5.2 (Register format) |
| Unity Catalog and Data Lifecycle Recommendations | Section 2.4 Domain 1 + 5.1 Per-Domain Assessment |
| Pilot Use Case Design and Implementation Evidence | Section 3 (Pilot) + 5.3 (Evidence package) |
| Performance and Scalability Validation Results | Section 3.4 (Success criteria) + Domain 5 assessment |
| Architecture Remediation Tracker and Completed Remediation Evidence | Section 4 (Remediation) + 5.4 (Tracker) |
| Day 1 Go-Live Architecture and Day 2 Roadmap Recommendations | Section 4.1 (Prioritization) + 5.5 (Day 1/Day 2) |
| Workstream B–E Handoff Package | Section 4.4 (Handoff) + 5.6 (Package contents) |