KPMG  ·  CVS HEALTH

Enterprise Observability and Security Data Foundation

Workstream D

Observability, Availability & Performance Monitoring Rationalization

Detailed Methodology

At a glance Systematically inventory, classify, and disposition 33,649 saved searches, 3,413 dashboards, 552 applications, and thousands of knowledge objects — retiring ~30–40% as technical debt and migrating high-value content to native Databricks (SQL, PySpark, Workflows, Dashboards) through an AI-accelerated factory model with before/after validation.

| Document | Detail |
| --- | --- |
| Program | Enterprise Observability & Security Data Foundation |
| Workstream | D — Observability, Availability & Performance Monitoring Rationalization |
| Supplements | SOW Section 2.7 |
| Timeline | 28 weeks (Inventory: 1–6 · Migrate: 7–24 · Validate: 22–28) |
| Scope | 33,649 searches · 3,413 dashboards · 552 apps · 45 data models |
| Target Output | Rationalization catalog + converted Databricks assets + validation evidence |
| Prepared by | KPMG |

Contents

1.0  Approach Overview	3

2.0  Splunk Content Rationalization Framework	4

2.1  The Three-Pillar Strategy	4

2.2  Rationalization Funnel	4

3.0  Saved Search Classification	5

3.1  Four-Category Classification	5

3.2  Category A — Migration Approach	5

3.3  Category B — Historical Analytics Migration	6

3.4  Category C — Cost Optimization Priority	6

3.5  Category D — Retirement Process	6

4.0  Dashboard Rationalization	7

4.1  Usage-Based Classification	7

4.2  Active Dashboard Migration Targets	7

4.3  Inactive Dashboard Review Process	7

5.0  Knowledge Object Rationalization	9

5.1  Object-by-Object Strategy	9

5.2  Dependency-Driven Retirement	9

6.0  Application Rationalization	10

6.1  Per-Application Migration Assessment	10

6.2  Application Disposition Categories	10

6.3  Splunk Enterprise Security (ES) Application	10

6.4  AIOps/ITSI Application	11

7.0  Migration Factory Model	12

7.1  Three-Phase Approach	12

7.2  SPL-to-Databricks Conversion Patterns	12

7.3  AI-Assisted Conversion	12

7.4  Conversion Capacity	13

8.0  Validation and Acceptance	14

8.1  Before/After Validation	14

8.2  Stakeholder Sign-Off	14

9.0  Alignment with SOW Scope and Deliverables	15

10.0  Coordination with Other Workstreams	15

1.0  Approach Overview

This document describes the detailed methodology KPMG will employ to rationalize and migrate selected analytics content from Splunk Enterprise into Databricks. It supplements SOW Section 2.7 (Workstream D) by providing the specific classification framework, rationalization workflow, migration approach, and validation process that enable systematic conversion of high-value Splunk content while retiring technical debt.

The Problem The CVS Splunk environment contains 33,649 saved searches, 3,413 dashboards, 552 applications, 45 data models, and thousands of supporting knowledge objects accumulated over years of platform operation. A significant portion of this content no longer provides active operational value. Migrating everything would replicate technical debt at scale and consume engineering effort that should be focused on business-critical content.

The Objective Systematically inventory, classify, and disposition all Splunk analytics content. Retire obsolete content (estimated 30–40% of the estate). Migrate high-value content to Databricks using a factory model that translates SPL queries, dashboards, reports, alerts, and accelerated data models into native Databricks equivalents (SQL, PySpark, Delta Tables, Workflows, Dashboards). Validate migrated content with business stakeholders before production deployment.

Relationship to Other Workstreams

- Workstream B1 provides data contracts that define the Bronze/Silver schemas WS-D queries will target

- Workstream C provides the Silver/Gold pipeline infrastructure and canonical data model that migrated analytics consume

- Workstream D’s dependency mapping directly informs B1 source disposition (sources without active analytics consumers become retirement candidates)

- Workstream E coordinates user adoption waves with content delivery milestones from WS-D

2.0  Splunk Content Rationalization Framework

2.1  The Three-Pillar Strategy

The rationalization strategy follows three sequential pillars, each reducing scope before engineering effort is invested:

Pillar 1 — Rationalization Identify and retire content that is obsolete, duplicated, or unused. Engineering effort is only invested in content that continues to deliver measurable operational or business value.

Pillar 2 — Consolidation Combine duplicate or overlapping content. Multiple searches, dashboards, or reports that serve the same business purpose are merged into single Databricks implementations.

Pillar 3 — Modernization Re-engineer retained content using native Databricks capabilities. SPL is converted to Databricks SQL/PySpark. Splunk dashboards become Databricks SQL Dashboards or BI tool outputs. Scheduled searches become Databricks Workflows or DLT pipelines. Data models become Silver/Gold tables.

2.2  Rationalization Funnel

33,649 Saved Searches + 3,413 Dashboards + 552 Apps + Knowledge Objects ¦ v CLASSIFY ¦ +-- Retire: ~12,667 disabled searches (38%) + ~983 inactive ¦ dashboards (29%) + unused apps + orphaned objects ¦ v CONSOLIDATE ¦ +-- Merge: Duplicate/overlapping content -> single Databricks impl. ¦ v MODERNIZE ¦ +-- Migrate: Active content -> Databricks SQL, PySpark, Workflows, Dashboards

3.0  Saved Search Classification

3.1  Four-Category Classification

Every saved search (33,649 total) is classified into one of four categories:

| Category | Description | Count | Disposition |
| --- | --- | --- | --- |
| A — Active Scheduled | Enabled scheduled searches executing without user interaction — generate alerts, open ServiceNow incidents, produce reports, execute compliance reporting, support automation | 15,159 | Primary migration candidates. Convert to Databricks Jobs, Workflows, or DLT pipelines while preserving existing outputs. |
| B — Historical Analytics | Searches routinely querying data beyond the planned Splunk hot-retention window — weekly, monthly, quarterly trend analysis, capacity planning, historical compliance | TBD | Migrate early. Databricks becomes the authoritative platform for long-term telemetry; these benefit most from cost-efficient historical storage. |
| C — High-Cost Scheduler | Searches with high execution frequency, long runtime, or significant data scan volumes — disproportionate Splunk infrastructure consumption | TBD | Prioritize for immediate cost relief. Migrating these provides licensing and infrastructure savings (reduces Splunk and Chronicle ISV costs). |
| D — Disabled (Retire) | Disabled or unused saved searches | 12,667 | Archive and retire. Catalog, associate with owner, approve for retirement, remove from production. Do NOT rebuild or migrate. |

3.2  Category A — Migration Approach

Active scheduled searches are ideal Databricks migration candidates because they execute without direct user interaction. The migration approach per search:

- Inventory: Extract search definition (SPL, schedule, actions, outputs, owner, app context)

- Dependency Map: Identify data sources (indexes, sourcetypes), knowledge objects (lookups, macros, event types), and outputs (alerts, reports, ServiceNow integrations)

- Target Schema Map: Map source indexes/sourcetypes to Bronze/Silver tables via B1 data contracts

- Translate: Convert SPL to Databricks SQL or PySpark targeting Silver/Gold schemas

- Configure: Set up Databricks Workflow with equivalent schedule, alerting, and output integrations

- Validate: Run parallel execution (Splunk + Databricks) to confirm output parity

- Cutover: Disable Splunk search, activate Databricks equivalent, monitor for issues

3.3  Category B — Historical Analytics Migration

Historical analytics migrate early because they benefit most from Databricks’ cost-efficient long-term storage:

- Weekly/monthly/quarterly reports → Databricks SQL Dashboards with scheduled refresh

- Capacity planning → Silver/Gold aggregate tables with historical trend queries

- Compliance reporting → Gold compliance evidence tables with automated report generation

3.4  Category C — Cost Optimization Priority

High-cost searches are identified by analyzing Splunk scheduler logs for:

- Execution frequency: Searches running every 1–5 minutes

- Runtime: Searches taking >30 seconds to execute

- Scan volume: Searches scanning >1 TB per execution

- Concurrency impact: Searches consuming disproportionate search head CPU/memory

These are prioritized for early migration regardless of business criticality because their removal provides immediate Splunk licensing and infrastructure relief.

3.5  Category D — Retirement Process

Disabled searches follow a controlled retirement workflow:

- Catalog: Record search name, owner, app, last execution date, associated indexes

- Archive: Export search definition to migration archive

- Notify: Contact application owner with retirement notice

- Approve: Owner confirms retirement (or silence after escalation = approval)

- Remove: Delete from Splunk production environment

- Document: Record retirement in rationalization catalog for audit trail

4.0  Dashboard Rationalization

4.1  Migration Strategy: Searches First, Visualization as Operational Task

Primary migration objective for dashboards is recreating the underlying searches and data logic — not pixel-perfect visualization replication. Most commonly used dashboards can be ported, but tailored dashboard visual recreation can shift to the user-side as an operational task rather than a project deliverable.

Approach:

- Migrate the searches: Convert the SPL queries powering dashboard panels to Databricks SQL. This is the engineering value — and it's already covered by the search migration factory (Section 10).

- Rebuild priority dashboards: Use telemetry (hit frequency by business group) to set a threshold. Dashboards above the threshold are rebuilt by KPMG/SciCom in Databricks SQL Dashboards.

- Last-mile dashboard creation → operational task: Remaining dashboards below the threshold are handed to CVS operations / SciCom as an ongoing operational activity. WS-E provides train-the-trainer support (Databricks SQL Dashboard builder training for L2–L3 Power Users).

- Programmatic acceleration: Dashboard panels can be constructed programmatically (akin to Power BI dashboard generation) — logic-to-logic matching is feasible. Visual inspection/validation that rebuilt dashboards match originals relies on multimodal AI comparison (bleeding-edge; acceleration factor varies).

Initial Threshold Determination:

- Dashboards accessed in last 7 days (1,295) → highest priority for KPMG-built migration

- Dashboards accessed in last 30 days but not 7 (1,135) → evaluate on case-by-case basis

- Dashboards not accessed in 30+ days (983) → retirement review or user-side recreation

4.2  Usage-Based Classification

Dashboard rationalization uses usage recency as the primary classification signal:

| Classification | Count | % | Action |
| --- | --- | --- | --- |
| Accessed within last 7 days | 1,295 | 38% | Highest operational priority. Evaluate for Databricks migration — supports daily operational decisions. |
| Accessed within last 30 days (but not 7) | 1,135 | 33% | Active operational. Evaluate for migration; may include weekly/monthly reporting. |
| Not accessed in 30+ days | 983 | 29% | Candidate for retirement. Business review required before disposition. |

4.3  Active Dashboard Migration Targets

Dashboards regularly used support the following operational functions and are evaluated for Databricks migration:

- NOC operations

- SOC operations

- SRE dashboards

- Infrastructure operations

- Application support

- Major incident management

- Historical trends and capacity planning

- Executive reporting

- Compliance evidence

4.4  Inactive Dashboard Review Process

The 983 dashboards not accessed in 30+ days are not automatically retired. Some may support infrequent but critical processes:

- Monthly, quarterly, or annual reporting

- Audit and compliance evidence

- Disaster recovery procedures

- Seasonal business processes

Each inactive dashboard undergoes business validation:

- Owner Identification: Identify the dashboard creator and business owner

- Dependency Check: Determine if other dashboards or reports depend on it

- Process Review: Confirm whether it supports periodic operational processes

- Regulatory Check: Verify any audit or compliance requirements

- Replacement Check: Determine if a newer dashboard has superseded it

- Disposition Decision: Migrate, retain in Splunk, or retire

Expected outcome

| Dashboard Disposition | Est. Population | Action |
| --- | --- | --- |
| Active dashboards | ~2,430 | Retain or migrate based on business need |
| Candidate inactive dashboards | ~983 | Business review required |
| Approved retirement | TBD (following owner review) | Archive and do not migrate |

5.0  Knowledge Object Rationalization

5.1  Object-by-Object Strategy

Knowledge objects are the glue between raw data and usable Splunk content. Each object type has a specific rationalization and migration strategy:

| Object Type | Count | Rationalization Strategy | Databricks Migration Target |
| --- | --- | --- | --- |
| Lookups | >1,000 | Migrate with owning application. Validate data freshness and usage. Retire stale lookups. | Unity Catalog managed tables or Delta tables; reference tables in Silver/Gold schemas. |
| Macros | 587 | Rewrite where referenced by migrating content. Retire macros only used by retired searches. | Databricks SQL UDFs, Notebook utility functions, or inline query logic. |
| Event Types | TBD* | Evaluate individually. Map to Silver-layer categorization logic. | WHERE clause filters or Silver table partition/column logic. |
| Tags | TBD* | Preserve as metadata. Tags represent business classification that should persist. | Unity Catalog tags, table properties, or Silver-layer enrichment columns. |
| Calculated Fields | TBD* | Implement within Silver transformations. Business logic currently embedded in search-time extraction. | DLT column expressions in Silver pipelines (WS-C). |
| Data Models | 45 | Re-engineer using Medallion architecture. Splunk’s acceleration framework replaced by Silver/Gold tables. | Silver domain tables (normalized, governed) + Gold analytical products. |
| KV Store Collections | 201 | Validate application dependency. Many support stateful lookups or dashboard state. | Delta tables with merge/upsert patterns; may require API-layer compatibility. |

*Require Splunk metadata export to determine

5.2  Dependency-Driven Retirement

Knowledge objects that are only referenced by retired searches or dashboards become retirement candidates themselves. The dependency analysis follows this logic:

For each knowledge object: Find all searches and dashboards that reference it If ALL referencing content is Category D (retired): -> Object is a retirement candidate If ANY referencing content is Category A, B, or C: -> Object must be migrated alongside that content If object is shared across multiple apps: -> Flag as high-priority migration dependency

6.0  Application Rationalization

6.1  Per-Application Migration Assessment

Each of the 552 Splunk applications receives a structured migration assessment:

| Assessment Element | Purpose |
| --- | --- |
| Associated indexes | Which data sources does this app consume? |
| Source families | Maps to B1 data contracts |
| Scheduled searches | Category A/B/C/D classification |
| Dashboards | Usage recency classification |
| Lookups | Data dependencies |
| Macros | Logic dependencies |
| KV Store dependencies | Stateful data requirements |
| User communities | Who uses this app? How many users? |
| Business criticality | Impact if unavailable |
| Recommended migration wave | Sequencing based on dependencies and priority |

6.2  Application Disposition Categories

| Disposition | Criteria | Action |
| --- | --- | --- |
| Migrate | Active users, active content, business-critical | Full content migration to Databricks (searches, dashboards, knowledge objects) |
| Partial Migrate | Some content active, some retired | Migrate active content, retire remainder |
| Retain in Splunk | Operational content that must remain in Splunk during hybrid period | No migration; ensure data is also available in Databricks for future migration |
| Retire | No active users, no active content, no business justification | Archive and decommission |

6.3  Splunk Enterprise Security (ES) Application

ES is treated as a special-case application due to its complexity and criticality:

- Correlation searches: Classify as Category A (active) or D (disabled). Active correlations are converted to Databricks SQL detection rules or Workflows.

- Notable events: Map to Databricks alerting + ServiceNow integration patterns.

- Risk framework: Evaluate for re-implementation using Silver/Gold risk scoring tables.

- Threat intelligence: Map to Databricks Delta tables with automated threat feed ingestion.

- ES dashboards: Migrate highest-use security dashboards to Databricks SQL Dashboards.

6.4  AIOps/ITSI Application

ITSI assets are assessed during WS-A and migrated where applicable:

- Service trees: Re-implement using Gold-layer service health models.

- KPI definitions: Convert to Databricks SQL metrics computed against Silver/Gold tables.

- Glass tables: Migrate to Databricks SQL Dashboards or BI tool visualizations.

- ML-driven alerts: Re-implement using Mosaic AI / MLflow against Silver/Gold feature sets.

7.0  Data Scope and Platform Segmentation

7.1  Scope Covers Three Distinct Splunk Domains

The Workstream D scope encompasses the full Splunk analytics estate across three platform domains. Each domain contributes distinct content types, complexity characteristics, and migration patterns:

| Platform Domain | Content Profile | Confirmed Volume | Complexity Driver |

|---|---|---|---|

| **Splunk Core (~85%)** | Saved searches, dashboards, operational reports, scheduled jobs, alerts, lookups, macros | 33,649 searches (15,159 active scheduled), 3,413 dashboards (2,430 active), 552 apps | Volume; diverse SPL patterns; multi-team ownership; 80% of active searches require alerting functionality |

| **Enterprise Security (~10%)** | Correlation searches, notable events, risk framework, threat intelligence, ES dashboards, compliance reporting | 3,800 saved searches, 3,059 scheduled, **234 enabled correlation searches** (150 CVS custom + 84 stock ES), 764 dashboards, 16 accelerated data models, 31 risk-based rules, 140 users | Specialized security logic; risk scoring; TSIDX summarization dependencies; threat feed integrations; regulatory constraints |

| **AI Ops / ITSI (~5%)** | Service trees, KPI definitions, glass tables, ML-driven alerts, anomaly detection | TBD (requires WS-A validation) | ML model dependencies; service topology; real-time health scoring |

**Sizing methodology must account for all three domains.** Sid's data analysis (SciCom Technical Implementation Approach, v1.0) covers the Splunk Core estate (~85% of volume). The ES Search Head Scoping Report (2026-07-14) provides validated ES numbers from live `| rest` queries. AI Ops remains pending WS-A validation.

**ES Detection Surface — Must-Migrate-First Tier:**

Of the 234 enabled correlation searches, only ~15 have fired to notable in the last 7 days. These represent the active detection surface and constitute the must-migrate-first tier. The remaining enabled correlations are detection coverage that must be preserved but may not require immediate parallel validation. The risk index generates 402,093 risk events/24h across 31 distinct risk rules — the RBA scoring pipeline must be preserved in the target.

**ES Two-Track Migration Approach:**

- **CVS Custom Correlations (150 / 64%):** Home-grown SPL requiring per-rule translation and SOC validation. Higher effort per rule.

- **Stock ES Correlations (84 / 36%):** Aligned to MITRE/CIM — translates more mechanically using pattern-based conversion.

7.2  Per-Domain Migration Characteristics

| Characteristic | Splunk Core | Enterprise Security | AI Ops / ITSI |
| --- | --- | --- | --- |
| SPL complexity | Low–Medium (standard search patterns) | Medium–High (correlation, risk scoring, multi-stage) | High (ML pipelines, anomaly detection, service dependency) |
| Validation requirements | Business stakeholder UAT | SOC validation + detection accuracy testing | Service health parity + ML model performance |
| Integration dependencies | ServiceNow, email, reporting | SOAR, threat feeds, incident response | CMDB service trees, monitoring infrastructure |
| Retirement opportunity | High (30–40% disabled/unused) | Lower (security content is compliance-driven) | Medium (ITSI assets may be superseded by Databricks native) |
| Effort multiplier (relative to Core baseline) | 1.0× | 1.5–2.5× | 2.0–3.0× |

7.3  Google Chronicle Scope

In addition to the Splunk estate, the migration scope includes Google Chronicle SIEM content currently managed by Farzana's security team:

| Component | Volume / Status | Migration Characteristics |
| --- | --- | --- |
| Data sources | ~170 sources | Same source-family → Bronze → Silver taxonomy applies |
| Detection rules | YARA-L rules + reference lists | Convert to PySpark / Databricks SQL detection logic |
| Parsers/mappings | UDM (Unified Data Model) mappings catalogued | Inventory in WS-D; map to Silver schemas |
| Queries/searches/dashboards | Counts held by Ryan (via Josh) — not yet verbally confirmed | Populate migration table once received |
| Daily volume | ~104 TB/day (Phase 1 prioritized sources) | Endpoint-heavy (Tanium ~68 TB, CrowdStrike ~16 TB) |

**Lower Risk / Near-Turnkey:** Farzana's team has already rebuilt much of the Chronicle detection capability in Databricks + AWS. KPMG can embed with her team or reuse their existing blueprint. This significantly reduces engineering effort relative to the Splunk Core migration.

**Chronicle Migration Approach:**

1. Inventory YARA-L detection rules and reference lists

2. Map UDM parsers to Bronze/Silver schemas (OCSF-aligned where applicable)

3. Convert YARA-L → PySpark/SQL using same Blaze factory model

4. Validate detection accuracy against Chronicle baseline

5. SOC acceptance and production deployment

**Chronicle is characterized as smaller and lower-risk than Splunk** — but must not be overlooked in the scope estimation. The same factory model, tooling, and validation process applies.

7.3  Data Model Acceleration Prerequisite (WS-C Dependency)

The ES Search Head operates 16 accelerated data models (DMAs) providing TSIDX summarization for core CIM domains. Correlation searches running against `tstats` today execute in seconds because they query pre-computed summary data rather than raw events.

**Without equivalent pre-aggregated Silver/Gold tables in Databricks, migrated ES correlation searches will degrade from sub-second to full-scan speeds.**

| Accelerated CIM Domain | Current Performance | Databricks Requirement |

|---|---|---|

| Authentication | `tstats` = seconds | Silver/Gold pre-aggregated auth table |

| Endpoint | `tstats` = seconds | Silver endpoint events (pre-joined with asset/identity) |

| Network_Traffic | `tstats` = seconds | Silver network sessions (vendor-neutral) |

| Malware | `tstats` = seconds | Silver malware events |

| Web | `tstats` = seconds | Silver web access |

| Change | `tstats` = seconds | Silver change events |

| Intrusion_Detection | `tstats` = seconds | Silver IDS/IPS events |

| Vulnerabilities | `tstats` = seconds | Silver vulnerability summary |

**Implication:** WS-C must deliver the Silver domain tables for these 16 CIM domains BEFORE WS-D can validate migrated ES correlation searches at production SLAs. This is a hard sequencing dependency — ES migration cannot complete until the summarization tier exists in Databricks.

8.0  Analytics Complexity and Effort Estimation Framework

8.1  Purpose

This section defines the structured framework for classifying analytics content by complexity and translating complexity into migration effort estimates. It addresses the key sizing question: given the rationalized content inventory (post-retirement, post-consolidation), how much engineering effort is required to migrate each item to Databricks?

The framework operates in two stages:

1. **Classify** — assign each analytics asset a complexity tier

2. **Estimate** — apply per-tier effort multipliers segmented by platform domain

8.2  Analytics Complexity Classification

Every retained analytics asset (search, dashboard, report, alert) is classified across five dimensions:

| Dimension | Low | Medium | High |

|---|---|---|---|

| **Data Sources** | Single index/sourcetype; maps to one Silver table | 2–3 source families; requires cross-table joins | 4+ source families; complex multi-domain correlation |

| **Transformation Logic** | Standard aggregations (stats, timechart); direct WHERE filters | Lookups, macros, eval chains, subsearches | Multi-stage pipelines, event types, calculated fields, custom commands, data model acceleration |

| **Operational Criticality** | Informational; failure is low-impact | Operational; drives alerts or team workflows | Mission-critical; drives incident response, compliance, or executive decisions |

| **Output Complexity** | Single result set or alert | Multiple outputs (report + alert + lookup update) | Complex integrations (SOAR, ServiceNow, automated remediation) |

| **Testing Requirements** | Row-count comparison sufficient | Aggregation parity + schedule validation | Full detection-accuracy testing, false-positive/negative analysis, parallel-run validation | 10.0  Migration Factory Model

8.3  Composite Complexity Tier Assignment

Each asset's five-dimension scores produce a composite complexity tier:

| Tier | Criteria | Est. Distribution (Core) | Migration Approach |

|---|---|---|---|

| **Low Effort** | All dimensions Low, or mostly Low with one Medium | ~50% of retained content (pending confirmation — may be 30%) | AI-assisted bulk translation via Blaze; minimal human review; automated validation |

| **Medium Effort** | Mix of Low and Medium dimensions; or single High dimension | ~30% of retained content (pending confirmation — may be 50%) | AI-assisted translation with KPMG engineer review; manual validation against Splunk output |

| **High Effort** | Multiple High dimensions; or any security/compliance-critical classification | ~20% of retained content (confirmed) | Custom engineering; dedicated design review; extended parallel validation; stakeholder sign-off |

**Note on Distribution:** The 20% complex tier is confirmed by Steve Koelpin (CVS Principal Observability Engineer). The split between Low and Medium is pending final confirmation (either 50/30 or 30/50). The 80% of active searches requiring alerting functionality (ServiceNow ticket generation, email notifications) pushes content toward Medium because alert integration adds output complexity beyond simple query conversion. Final distribution will be confirmed following Steve's detailed analysis.

**SPL Complexity Shorthand (Sid's sizing model):**

- **Easy (Low):** Few lines of SPL; standard `stats`, `where`, `timechart` patterns; single index/sourcetype

- **Medium:** 10–20 lines of SPL; lookups, macros, eval chains, subsearches; 2-3 source families

- **Complex (High):** ~50+ lines of SPL; multi-stage pipelines, custom commands, data model acceleration, event correlation

8.4  Composite Complexity Tier Assignment

| Asset Type | Low Effort | Medium Effort | High Effort |

|---|---|---|---|

| **Saved Search → Databricks Job** | 1–4 hrs | 8–16 hrs | 24–40 hrs |

| **Dashboard → SQL Dashboard** | 4–8 hrs | 16–24 hrs | 40–60 hrs |

| **Alert → Workflow + Notification** | 2–4 hrs | 8–12 hrs | 16–24 hrs |

| **Data Model → Silver/Gold Tables** | 8–12 hrs | 20–30 hrs | 40–60 hrs |

| **KV Store → Delta Table** | 2–4 hrs | 8–12 hrs | 16–24 hrs |

**Effort includes:** translation, configuration, testing, validation, and documentation. Testing typically doubles raw conversion time (~80% pass first attempt; 20% require rework cycle).

8.5  Platform Domain Effort Multipliers

Base effort estimates (Section 8.4) apply to Splunk Core content. Enterprise Security and AI Ops content applies a multiplier reflecting increased complexity, validation requirements, and integration dependencies:

| Platform Domain | Effort Multiplier | Rationale |

|---|---|---|

| Splunk Core | 1.0× | Baseline — standard operational searches and dashboards |

| Enterprise Security (ES) | 1.5–2.5× | Correlation logic complexity, detection accuracy validation, threat feed integration, compliance constraints |

| AI Ops / ITSI | 2.0–3.0× | ML model retraining, service topology recreation, anomaly detection calibration, real-time health parity |

8.6  Sizing Inputs Required from CVS

The framework produces defensible estimates only when populated with validated data. The following inputs are required from CVS (via direct engagement, not intermediary estimates):

| Required Input | Source | Purpose | Fallback if Unavailable |

|---|---|---|---|

| Active search count by platform (Core/ES/AI Ops) | Splunk scheduler logs + ES/ITSI admin consoles | Total migration volume per domain | Estimate from metadata exports (lower confidence) |

| Search complexity distribution | SPL analysis (macro usage, subsearch depth, lookup count) | Tier assignment (Low/Med/High) | Sample-based extrapolation from 50–100 representative searches |

| Dashboard access logs (30/60/90 day) | Splunk internal indexes (_audit, _internal) | Retirement vs. migration classification | Owner-confirmed disposition per dashboard |

| ES correlation search inventory | ES admin console export | ES-specific volume and complexity | Sid's partial inventory + extrapolation |

| ITSI service tree and KPI inventory | ITSI admin console export | AI Ops scope validation | WS-A assessment output |

| Owner/team mapping per application | Splunk application metadata + org directory | Stakeholder validation planning | Escalation-based ownership discovery |

8.7  Estimation Workflow

Step 1: Inventory Export full search/dashboard/alert inventory across Core + ES + AI Ops │ Step 2: Rationalize (Sections 2–6) Apply retirement (~30–40%) + consolidation (2x–10x reduction TBD) → Produces RETAINED migration backlog │ Step 3: Classify Complexity Score each retained item across 5 dimensions (Section 8.2) Assign composite tier: Low / Medium / High │ Step 4: Segment by Platform Tag each item: Core / ES / AI Ops Apply platform multiplier (Section 8.5) │ Step 5: Calculate Effort Per-item effort = Base hours (Section 8.4) × Platform multiplier (Section 8.5) Total effort = Σ per-item effort across full backlog │ Step 6: Validate Against Capacity Compare total effort to available team capacity and SOW timeline Identify Phase 1 scope boundary (deliverable within current engagement) Quantify remaining effort for subsequent phases / Change Orders

8.8  Illustrative Sizing Scenario

*Note: These are illustrative figures for methodology demonstration. Actual estimates will be populated following pre-assessment data collection and SME validation.*

| Step | Splunk Core | Enterprise Security | AI Ops | Total |

|---|---|---|---|---|

| Raw inventory | 30,000 searches | 2,500 searches | 1,149 assets | 33,649 |

| After retirement (35%) | 19,500 | 2,000 | 750 | 22,250 |

| After consolidation (est. 3×) | 6,500 | 1,200 | 500 | 8,200 |

| Low effort (50%/30%/20%) | 3,250 | 360 | 100 | 3,710 |

| Medium effort (30%/40%/30%) | 1,950 | 480 | 150 | 2,580 |

| High effort (20%/30%/50%) | 1,300 | 360 | 250 | 1,910 |

*Effort distribution shifts toward Medium/High for ES and AI Ops due to inherent complexity.*

9.0  Source Rationalization and Governance

9.1 How Data Sources Are Rationalized

Before analytics migration can be sized, the underlying source landscape must be rationalized. This workstream consumes WS-B1's source rationalization output but also contributes to it:

| Activity | WS-D Contribution | WS-B1 Dependency |

|---|---|---|

| Identify overlapping data sources | Dependency mapping reveals which sources serve same analytics purpose | B1 identifies duplicate source families at the schema level |

| Determine authoritative sources | Analytics content usage reveals which source is "primary" for a given business question | B1 confirms via source-owner validation |

| Establish data contracts for analytics | D's converted queries define the Silver/Gold schemas they target | B1 authors the formal ODCS contract governing that schema |

9.2 Source Owner Validation and Governance

Sid and the team have identified that reliable sizing depends on validation from actual data owners — not intermediary estimates. The following governance process ensures assumptions are validated:

1. **Identify Source Owners:** Map each application/source family to its business and technical owner (Chris Robinson, Charles "Chuck" Markham identified as key contacts for data details and metrics)

2. **Structured Validation Sessions:** Conduct owner-by-owner review of:

- Active vs. stale content per source

- Business criticality classification

- Consolidation candidates (multiple searches serving same purpose)

- Retirement approvals

3. **Assumption Sign-Off:** Document and obtain owner confirmation for:

- Search counts per platform domain

- Complexity tier assignments

- Retirement candidates

- Consolidation opportunities

4. **Ongoing Governance:** Establish review cadence during migration execution to validate conversion accuracy and detect scope changes

10.0  Migration Factory Model

10.1  Three-Phase Approach

| Phase | Duration | Focus | Output |
| --- | --- | --- | --- |
| Inventory & Classify | Weeks 1–6 | Full content inventory, Category A–D classification, dashboard usage analysis, dependency mapping, application assessments | Rationalization catalog, prioritized migration backlog |
| Migrate & Convert | Weeks 7–24 | SPL → SQL/PySpark conversion, dashboard rebuild, workflow configuration, knowledge object migration, parallel validation | Converted Databricks assets, validation evidence |
| Validate & Handover | Weeks 22–28 | Business stakeholder validation, UAT, before/after evidence, sign-off, documentation | Accepted production assets, migration handoff docs |

10.2  SPL-to-Databricks Conversion Patterns

| Splunk Construct | Databricks Equivalent | Conversion Approach |
| --- | --- | --- |
| index= / sourcetype= | FROM silver.<domain_table> | Map via B1 data contracts to Silver/Gold schemas |
| search / where | WHERE clause | Direct SPL-to-SQL translation |
| stats / chart / timechart | GROUP BY / aggregate functions | SQL aggregation patterns |
| eval | SELECT computed columns | Inline expressions or UDFs |
| lookup | JOIN against Delta table | Lookup tables migrated to Unity Catalog |
| macro | UDF or CTE | Macro logic expanded or converted to function |
| tstats (accelerated) | Query against Silver/Gold pre-aggregated table | Acceleration replaced by materialized Silver/Gold views |
| ¦ outputlookup | MERGE INTO / INSERT OVERWRITE | Delta merge patterns |
| ¦ sendalert | Databricks Workflow + notification action | Alert action configuration |
| cron schedule | Databricks Workflow schedule | Schedule configuration |
| Dashboard XML/JSON | Databricks SQL Dashboard | Dashboard rebuild using SQL queries |

10.3  AI-Assisted Conversion (KPMG Blaze)

KPMG Blaze is a containerized, LangChain-based agentic platform that orchestrates agents across requirements, design, code, and test generation with human-in-the-loop review. Unlike naive SPL-to-SQL transpilers that perform 1:1 syntax translation, Blaze addresses the fundamental data model reconstruction challenge: understanding how data must be reshaped, joined, and aggregated in Databricks so that converted queries return correct results.

**Core Workflow — Learn → Derive → Optimize → Refactor:**

KPMG Blaze and AI-assisted transpiler tooling accelerates SPL-to-SQL conversion:

```

Step 1: Knowledge Base Ingestion

Ingest SPL queries + associated context (indexes, sourcetypes, lookups,

macros, data models, field extractions) into Blaze Knowledge Base

│

Step 2: Code Summary & Dependency Decomposition

Automated decomposition of legacy analytics content into logical components.

LLM-generated summaries of dependencies, business functions, and cross-query

relationships. Surfaces dead code, duplicated detections, and rationalization

candidates.

│

Step 3: Data Model Derivation

Blaze analyzes HOW queries consume data — what fields they join on, what

they aggregate, what implicit contracts exist — and derives the underlying

data model that makes those queries work. This is the critical step that

addresses the schema-on-read → schema-on-write gap.

│

Step 4: Data Model Optimization

Proposes simplified and consolidated schemas. Multiple queries targeting

overlapping data are analyzed together to produce an optimized Silver/Gold

schema that serves all consumers with less redundancy.

│

Step 5: Query Refactoring & Code Generation

Generates target-state Databricks SQL/PySpark against the optimized data

model. Produces both data ingestion pipelines (Bronze → Silver) and

converted analytics queries (targeting Silver/Gold).

│

Step 6: Test Case Generation & Automated Validation

Produces test cases comparing Splunk output vs. Databricks output.

Automated before/after comparison for row counts, aggregated values,

and result structure.

│

Step 7: Human Review Gate

All AI-generated outputs pass through mandatory KPMG engineer review.

Security-critical content (ES correlations, compliance) requires additional

SOC/stakeholder validation before production deployment.

```

**Blaze Capabilities Applied to WS-D:**

| Capability | WS-D Application | Acceleration |

|---|---|---|

| **Knowledge Base** | Grounded context layer combining ingested SPL, Cribl packs, data models, and client schemas. Anchors outputs in CVS's actual estate. | Reduces hallucination; ensures schema fidelity |

| **Code Summary** | Automated decomposition of 15,159 active searches into logical components with dependency summaries | Compresses discovery; surfaces rationalization candidates |

| **Knowledge Graph** | Visual dependency mapping across searches, dashboards, lookups, macros, and data models | Replaces weeks of manual dependency analysis |

| **Agentic Chat** | Engineers query legacy content behavior in natural language without waiting on Splunk SMEs | Shortens onboarding; reduces SME bottleneck |

| **Modernize** | Generates Databricks SQL, PySpark, Workflow configs, and test suites with human-in-the-loop | Core conversion engine |

**Why This Matters:**

Simply converting SPL syntax to SQL addresses approximately 0.3% of the migration problem. The remaining 99% is understanding how the data is combined, aggregated, and structured behind those queries — particularly when Splunk's schema-on-read flexibility allows queries to reference fields that don't formally exist until search-time extraction. Blaze's "learn → derive → optimize → refactor" workflow solves this by treating data model reconstruction as the primary objective, not an afterthought.

**Measured Efficiency:**

- 40–60% reduction in delivery cost relative to manual conversion

- ~50% reduction in implementation timeline

- Deployed successfully at: $2T GSE mortgage lender (legacy app transformation), leading regional bank (data lineage), global healthcare services company (data pipeline modernization)

10.4  Conversion Capacity and Throughput Model

** Engineer Output Model**

| Metric | Target | Basis |

|---|---|---|

| Engineering team size | ~20 engineers | KPMG + SciCom joint delivery pods |

| Validated migrations per engineer per day | ~5 (including rework/retesting) | Steve's assessment: "reasonable but unconfirmed until proven in practice" |

| **Daily throughput (team)** | **~500 validated searches/day** | 20 × 25 per day |

| Weekly throughput | ~2,500 | 5 working days |

| Monthly throughput | ~10,000 | 4 working weeks |

| **15k active searches at full velocity** | **~30 working days (~6 weeks)** | Assumes steady-state; ramp-up extends timeline |

**Blaze Acceleration Applied:**

| Conversion Tier | Volume (est.) | Without Blaze | With Blaze (40-60% efficiency) | Approach |

|---|---|---|---|---|

| Auto-convertible (~30%) | ~4,500 searches | 2-4 hrs each | <1 hr each (review only) | Blaze bulk translation; automated validation |

| AI-assisted + human review (~50%) | ~7,500 searches | 8-16 hrs each | 4-8 hrs each | Blaze generates; KPMG engineer reviews and validates |

| Manual rewrite (~20%) | ~3,000 searches | 24-40 hrs each | 16-24 hrs each | Custom engineering with Blaze assistance for test generation |

**Caveats:**

- Throughput assumes Silver/Gold schemas are available (WS-C dependency)

- ES correlation searches run at lower throughput due to SOC validation requirements

- First 2-3 weeks operate at reduced velocity during team ramp-up and pattern establishment

- Consolidation (pre-conversion) may reduce the 15k count by 2×-10× — actual conversion volume is post-consolidation

11.0  Validation and Acceptance

11.1  Before/After Validation

Every migrated asset undergoes before/after comparison:

- Query Output Parity: Execute the original SPL in Splunk and the converted SQL in Databricks against the same time window. Compare row counts, aggregated values, and result structure.

- Alert/Action Parity: Confirm that Databricks Workflow produces equivalent alerting and notification behavior.

- Dashboard Visual Parity: Compare Splunk dashboard panels with Databricks SQL Dashboard panels for equivalent visualization and data representation.

- Performance Comparison: Measure query execution time in both platforms. Document cases where Databricks outperforms or underperforms Splunk.

11.2  Stakeholder Sign-Off

Each migrated content package (grouped by application or business domain) requires formal stakeholder acceptance:

- KPMG delivers migration package with before/after evidence

- Business stakeholder conducts UAT in Databricks

- Stakeholder confirms functional parity or documents exceptions

- Exceptions resolved or accepted as known limitations

- Formal sign-off recorded in migration tracker

12.0  Alignment with SOW Scope and Deliverables

| SOW Deliverable | Methodology Section |
| --- | --- |
| Splunk Analytics Inventory and Ownership Matrix | Section 2 (Rationalization Framework) + Section 7.1 (Inventory phase) |
| Rationalization and Prioritization Assessment | Section 3 (Search Classification) + Section 4 (Dashboard) + Section 5 (Knowledge Objects) |
| Splunk Apps, TAs and Modules Inventory and Disposition Matrix | Section 6 (Application Rationalization) |
| Query Conversion Tracker and Migration Backlog | Section 7 (Migration Factory) |
| Converted Databricks SQL/PySpark Assets | Section 7.2 (Conversion Patterns) |
| Migrated Dashboards, Reports and Alerts | Section 4 + Section 7 |
| Recreated Accelerated Data Model Outputs | Section 5.1 (Data Models → Silver/Gold) |
| ES/AIOps Content Migration Evidence | Section 6.3 (ES) + Section 6.4 (ITSI) |
| Validation Results and Before/After Evidence | Section 8 (Validation) |
| Migration and Handoff Documentation | Section 8.2 (Sign-Off) |

13.0  Coordination with Other Workstreams

| Workstream | Dependency Direction | Coordination Point |
| --- | --- | --- |
| B1 → D | B1 source contracts define which Silver/Gold tables D’s converted queries target | D cannot finalize query translation until B1 provides schema contracts for the relevant source families |
| C → D | C builds the Silver/Gold tables and pipeline infrastructure that D’s content consumes | D’s converted queries must be validated against actual Silver/Gold table outputs from C |
| D → B1 | D’s dependency mapping reveals which source families have active analytics consumers | Source families with no active D content are B1 retirement candidates |
| D → E | D’s content migration milestones define when users can be migrated | E’s adoption waves are sequenced to match D’s content delivery |
| A → D | A’s assessment validates AIOps/ITSI scope and ES architecture | D’s ES/ITSI migration scope is confirmed after A completes |

14.0  SPL-to-Databricks Conversion Considerations

14.1  Schema-on-Read → Schema-on-Write

Splunk operates on a schema-on-read model where fields are extracted dynamically at search time. Queries reference fields that may not formally exist until the search executes. Databricks operates on schema-on-write — fields must be explicitly defined in Silver/Gold schemas BEFORE queries can run against them.

This means SPL-to-SQL translation is not primarily a syntax problem. It is a data model reconstruction problem. The underlying datasets must be reshaped, joined, and aggregated in Databricks so that converted queries return correct results. Simply converting SPL syntax to SQL addresses approximately 0.3% of the migration challenge. Rebuilding the correct underlying data structures is the remaining 99%.

14.2  Specific Technical Considerations

| Challenge | Details | Resolution Pattern |

|---|---|---|

| **Schema-on-read → schema-on-write** | Splunk infers fields at search time; Databricks needs them pre-defined in Silver/Gold tables. The data model must be reconstructed from query semantics. | Blaze derives the target schema FROM the queries (learn → derive model → optimize → refactor) |

| **Implicit data relationships** | SPL joins across indexes/sourcetypes using field name collisions (no explicit FK). Same field name in different sourcetypes may carry different semantics. | Knowledge Graph maps dependencies; Silver schemas define explicit join keys via conformed dimensions |

| **tstats / Data Model Acceleration** | 16 ES data models provide TSIDX pre-computation. Correlation searches depend on this for sub-second performance. Without equivalent Silver/Gold pre-aggregates, searches degrade to full-scan. | WS-C must build equivalent Silver domain tables BEFORE ES migration completes (Section 7.4) |

| **SPL commands without SQL equivalents** | `transaction` (stateful event grouping), `streamstats` (running calculations), `eventstats` (append stats to events), `appendpipe`, `map`, `multisearch`, `dedup` with complex keep logic, custom search commands | PySpark UDFs for stateful operations; multi-step Workflow orchestration; Delta merge patterns for stateful accumulation |

| **Macro and lookup dependency chains** | SPL macros invoke other macros which reference lookups which reference KV Stores. The entire dependency graph must be resolved before any single query can be translated correctly. | Blaze Knowledge Base ingests full dependency graph; resolves transitive dependencies before translation |

| **Subsearch semantics** | SPL subsearches execute independently and feed results as filters to the outer search. No direct Databricks equivalent exists for this execution model. | CTEs (Common Table Expressions), temporary views, or multi-stage Workflow steps |

| **Risk-Based Alerting (RBA)** | ES risk framework accumulates risk scores across multiple contributing rules over configurable time windows. This is stateful — scores persist and decay. | Delta table with merge/upsert pattern; scheduled Workflow aggregates contributing scores; threshold triggers via Databricks SQL Alerts |

| **Splunk time windowing** | `earliest`/`latest` relative modifiers, `bin span=` for time bucketing, and rolling window aggregations have different edge-case semantics than SQL `BETWEEN` or `WINDOW` functions. | Explicit timestamp filtering with timezone handling; SQL WINDOW functions with careful frame specification; edge-case validation during testing |

| **Search-time field extraction** | Splunk `EXTRACT` and `REPORT` configurations create fields that only exist at search time. Queries depend on fields that aren't stored anywhere. | Promote extraction logic into Silver DLT transformations; fields become physical columns in Silver tables |

| **Event type and tag inheritance** | SPL event types apply layered classification (tags, event types, inherited fields) that accumulate across multiple configuration layers. | Flatten into Silver-layer categorization columns; or replicate as Unity Catalog tags/properties |

14.3  Specific Technical Considerations

Based on the complexity profile and Blaze capabilities, the migration factory triages content into three conversion tracks:

| Track | % of Retained Content | Effort Profile | Approach |

|---|---|---|---|

| **Auto-convert** | ~30% | Simple SPL patterns (single sourcetype, standard aggregations, no macros/lookups) | Blaze bulk translation → automated validation → minimal human review |

| **AI-assisted + human review** | ~50% | Moderate SPL (lookups, macros, eval chains, 2-3 sources, alerting integration) | Blaze generates candidate conversion → KPMG engineer reviews and corrects → manual validation against Splunk output |

| **Manual rewrite** | ~20% | Complex SPL (multi-stage, custom commands, DMA-dependent, RBA, SOAR integration) | Custom engineering with Blaze assistance for test generation; dedicated design review; extended parallel validation |

14.4  Patterns That Convert Cleanly vs. Patterns That Don't

**High-confidence auto-conversion (Easy):**

- `index=<single> sourcetype=<single> | stats count by field | where count > threshold`

- `index=<single> | timechart span=1h count by sourcetype`

- Simple `eval` expressions with standard math/string functions

- Basic `lookup` against static CSV (becomes JOIN against Delta table)

- Standard alert thresholds with email notification

**Requires engineering judgment (Medium):**

- Multi-index searches with implicit field joins

- `transaction` with maxspan/maxpause (requires PySpark session windowing)

- `streamstats` / `eventstats` (requires WINDOW functions with specific frame logic)

- Nested macros (must resolve dependency chain before translation)

- Searches with conditional `| where` logic dependent on `eval` chains

- ServiceNow integration via `sendalert` (must map to Databricks Workflow + REST action)

**Requires custom design (Complex):**

- ES correlation searches with risk scoring and multi-stage notable event generation

- ITSI KPI searches with ML-driven thresholding

- Custom search commands (Python/Java) with no Databricks equivalent

- Searches depending on accelerated data models (`tstats` against `datamodel`)

- Multi-search (`| append`, `| join`, `| multisearch`) patterns with complex merge logic

- SOAR-integrated response actions

- Searches that write state to KV Store and read it back in subsequent executions

15.0  Architectural Considerations — Out-of-Scope Enhancements

15.1 Elasticsearch / Lucene Sidecar Index — Interactive Search Tier

**The Potential Gap:**

Databricks SQL is optimized for structured analytical queries, scheduled detection, cross-domain correlation, and machine learning. It may not replicate all of Splunk's sub-second interactive full-text search capability over raw, semi-structured log data at terabyte scale. SOC analysts performing ad-hoc threat hunting, incident investigation, and regex-based pattern discovery depend on this interactive search capability daily.

Once Splunk is decommissioned, this gap becomes operationally visible. Databricks provides superior analytics, ML, and historical correlation — but cannot replace the "grep at scale" paradigm that security analysts rely on for unstructured investigation.

**The Pattern:**

An Elasticsearch (or OpenSearch) sidecar index deployed alongside the Databricks Lakehouse provides:

| Capability | Elasticsearch Sidecar | Databricks Lakehouse |

|---|---|---|

| Interactive full-text search | Sub-second across raw logs | Not optimized — seconds to minutes for text search |

| Regex / wildcard pattern matching | Native inverted index support | Possible but expensive (full scan) |

| Ad-hoc hunting (SOC) | Primary use case | Not designed for this |

| Hot-tier retention | 7–30 days (configurable) | All data (Bronze through Gold) |

| Structured analytics | Limited | Primary strength |

| Cross-domain correlation | Limited | Primary strength |

| Historical analysis (months/years) | Not cost-effective | Primary strength |

| ML / AI | Not applicable | Native (Mosaic AI, MLflow) |

**Architecture:**

```

Enterprise Sources

│

▼

Cribl Stream (dual-route)

│                    │

▼                    ▼

ADLS Gen2              Elasticsearch Cluster

│                    │

▼                    ▼

Databricks Bronze      Interactive Search

│                  (7-30 day hot tier)

▼                    │

Silver → Gold           ▼

(Analytics, ML,       Kibana / OpenSearch Dashboards

Detection,           (SOC investigation UX)

Correlation)

```

Cribl simultaneously routes telemetry to both ADLS Gen2 (for Databricks Bronze ingestion) and Elasticsearch (for interactive hot-tier search). The two systems serve complementary purposes:

- **Databricks:** Authoritative analytics platform for detection, correlation, reporting, ML, Gold products, and long-term historical analysis

- **Elasticsearch:** Interactive investigation tier for SOC ad-hoc hunting, regex search, and real-time pattern discovery

**Why Out-of-Scope:**

The current SOW focuses on migrating analytics content (searches, dashboards, alerts) from Splunk to Databricks and establishing the Lakehouse data foundation. The Elasticsearch sidecar is an operational architecture enhancement that extends the platform for interactive investigation use cases. It does not block the analytics migration but will be needed before Splunk can be fully decommissioned for SOC teams.

**Recommendation:** Flag during WS-A architecture assessment. If assessment confirms SOC teams require sub-second ad-hoc search (highly likely), recommend the sidecar pattern as a future phase deliverable addressable via Change Order. Alternatively, evaluate Databricks Vector Search + AI agents as a partial substitute for semantic log search (cannot match inverted-index performance for exact-match/regex at TB scale, but may satisfy a subset of investigation use cases).

**Estimated Effort (Future Phase):** Architecture design + Cribl routing configuration + Elasticsearch cluster provisioning + Kibana/OpenSearch Dashboards configuration + SOC workflow integration. Moderate effort; primary dependency is infrastructure provisioning rather than engineering complexity.